## Pour Log
QMix Logbook · Lalas Tower 22
Job: P9011 · Client: ADAC · Contractor: Quollnet · Consultant: Acme Counsult · Spec: ITP-CON-022 · Exported: 26 Jun 2026
TOTAL POURS |  | TOTAL VOLUME (m³) |  | DATE RANGE |  |  | POUR STATUS
22 |  | 2226.0 |  | 24 Jun 2026 |  |  | 1 Accepted · 18 Pending · 3 Rejected
# | DATE | LOCATION / ELEMENT | MIX GRADE / CODE | TICKET / TRUCK | QTY (m³) | SLUMP (mm) | TEMP (°C) | SAMPLES | STATUS | REMARKS / QA NOTES
1 | 24 Jun 2026 13:00 – 17:00 | Foundation Zone 1 Pile cap | C40 AD Mix 012 | Tkt: TAR-52-02 Trk: TAR-52 | 8m3 | Target: 100 Actual: 98 | C: 35° A: 40° | Yes / 2 pcs / Cubes PC-FD1-01, PC-FD1-02 | Pending | Admixture: Retarder Batch time: 15 min
2 | 24 Jun 2026 13:00 – 17:00 | Foundation Zone 1 Pile cap | C40 AD Mix 012 | Tkt: TAR-52-03 Trk: TAR-51 | 8m3 | Target: 100 Actual: 98 | C: 35° A: 40° | Yes / 2 pcs / Cubes PC-FD1-01, PC-FD1-02 | Accepted | Admixture: Retarder Batch time: 20 min
3 | 24 Jun 2026 14:40 – 15:20 | Foundation Zone 1 Pile cap | C40 AD Mix 012 | Tkt: TAR-52-04 Trk: TAR-58 | 10m3 | Target: 100 Actual: 110 | C: 28.5° A: 36.0° | Yes / 6 pcs / Cubes PC-FD1-03A to 03F | Rejected | Slump within acceptable tolerance (+/-20mm). Admixture: Retarder Batch time: 25 min
4 | 24 Jun 2026 15:10 – 15:55 | Foundation Zone 1 Pile cap | C40 AD Mix 012 | Tkt: TAR-52-05 Trk: TAR-62 | 10m3 | Target: 100 Actual: 95 | C: 29.0° A: 35.5° | No | Accepted with comments | Truck delayed slightly in site traffic. Temperature high but within spec limit (<30C). Admixture: Retarder Batch time: 35 min
5 | 24 Jun 2026 15:45 – 16:20 | Foundation Zone 1 Pile cap | C40 AD Mix 012 | Tkt: TAR-52-06 Trk: TAR-44 | 10m3 | Target: 100 Actual: 105 | C: 28.2° A: 35.0° | No | NCR opened | Admixture: Retarder Batch time: 28 min
6 | 24 Jun 2026 16:05 – 16:45 | Foundation Zone 1 Pile cap | C40 AD Mix 012 | Tkt: TAR-52-07 Trk: TAR-12 | 10m3 | Target: 100 Actual: 100 | C: 28.0° A: 34.8° | No | Pending | Excellent consistency. Admixture: Retarder Batch time: 30 min
7 | 24 Jun 2026 16:30 – 17:15 | Foundation Zone 1 Pile cap | C40 AD Mix 012 | Tkt: TAR-52-08 Trk: TAR-09 | 10m3 | Target: 100 Actual: 80 | C: 28.9° A: 34.2° | Yes / 6 pcs / Cubes PC-FD1-04A to 04F | Pending | Slump low due to site waiting time, but acceptable within lower limit. Admixture: Retarder Batch time: 42 min
8 | 24 Jun 2026 17:00 – 17:35 | Foundation Zone 1 Pile cap | C40 AD Mix 012 | Tkt: TAR-52-09 Trk: TAR-33 | 10m3 | Target: 100 Actual: 115 | C: 27.6° A: 33.5° | No | Pending | Dispatched from backup Plant 2. Check mix ticket code. Admixture: Retarder Batch time: 22 min
9 | 24 Jun 2026 17:25 – 18:05 | Foundation Zone 1 Pile cap | C40 AD Mix 012 | Tkt: TAR-52-10 Trk: TAR-58 | 10m3 | Target: 100 Actual: 105 | C: 27.4° A: 33.0° | No | Pending | Truck TAR-58 returned for second rotation. Admixture: Retarder Batch time: 26 min
10 | 24 Jun 2026 17:50 – 18:30 | Foundation Zone 1 Pile cap | C40 AD Mix 012 | Tkt: TAR-52-11 Trk: TAR-70 | 12m3 | Target: 100 Actual: 90 | C: 27.1° A: 32.4° | Yes / 6 pcs / Cubes PC-FD1-05A to 05F | Pending | 12m3 high-capacity trailer truck. Admixture: Retarder Batch time: 31 min
11 | 24 Jun 2026 18:15 – 18:50 | Foundation Zone 1 Pile cap | C40 AD Mix 012 | Tkt: TAR-52-12 Trk: TAR-62 | 10m3 | Target: 100 Actual: 100 | C: 26.9° A: 31.8° | No | Pending | TAR-62 second rotation. Admixture: Retarder Batch time: 24 min
12 | 24 Jun 2026 18:40 – 19:20 | Foundation Zone 1 Pile cap | C40 AD Mix 012 | Tkt: TAR-52-13 Trk: TAR-44 | 10m3 | Target: 100 Actual: 95 | C: 26.5° A: 31.2° | No | Pending | Admixture: Retarder Batch time: 29 min
13 | 24 Jun 2026 19:05 – 19:40 | Foundation Zone 1 Pile cap | C40 AD Mix 012 | Tkt: TAR-52-14 Trk: TAR-12 | 10m3 | Target: 100 Actual: 100 | C: 26.2° A: 30.5° | Yes / 6 pcs / Cubes PC-FD1-06A to 06F | Pending | Night pour setup completed. Lighting units active. Admixture: Retarder Batch time: 33 min
14 | 24 Jun 2026 19:30 – 20:05 | Foundation Zone 1 Pile cap | C40 AD Mix 012 | Tkt: TAR-52-15 Trk: TAR-09 | 10m3 | Target: 100 Actual: 110 | C: 25.9° A: 30.0° | No | Pending | Admixture: Retarder Batch time: 25 min
15 | 24 Jun 2026 19:55 – 20:35 | Foundation Zone 1 Pile cap | C40 AD Mix 012 | Tkt: TAR-52-16 Trk: TAR-35 | 10m3 | Target: 100 Actual: 85 | C: 26.3° A: 29.7° | No | Pending | Plant 2 delivery. Slump slightly low due to transit distance. Admixture: Retarder Batch time: 38 min
16 | 24 Jun 2026 20:20 – 20:55 | Foundation Zone 1 Pile cap | C40 AD Mix 012 | Tkt: TAR-52-17 Trk: TAR-58 | 10m3 | Target: 100 Actual: 105 | C: 25.6° A: 29.4° | Yes / 6 pcs / Cubes PC-FD1-07A to 07F | Pending | Admixture: Retarder Batch time: 23 min
17 | 24 Jun 2026 20:45 – 21:25 | Foundation Zone 1 Pile cap | C40 AD Mix 012 | Tkt: TAR-52-18 Trk: TAR-70 | 12m3 | Target: 100 Actual: 100 | C: 25.4° A: 29.1° | No | Pending | 12m3 load. Admixture: Retarder Batch time: 27 min
18 | 24 Jun 2026 21:10 – 21:45 | Foundation Zone 1 Pile cap | C40 AD Mix 012 | Tkt: TAR-52-19 Trk: TAR-62 | 10m3 | Target: 100 Actual: 110 | C: 25.2° A: 28.8° | No | Pending | Admixture: Retarder Batch time: 21 min
19 | 24 Jun 2026 21:35 – 22:10 | Foundation Zone 1 Pile cap | C40 AD Mix 012 | Tkt: TAR-52-20 Trk: TAR-44 | 10m3 | Target: 100 Actual: 95 | C: 25.1° A: 28.5° | Yes / 6 pcs / Cubes PC-FD1-08A to 08F | Pending | Final sampling set for foundation zone 1. Admixture: Retarder Batch time: 29 min
20 | 24 Jun 2026 22:00 – 22:30 | Foundation Zone 1 Pile cap | C40 AD Mix 012 | Tkt: TAR-52-21 Trk: TAR-12 | 10m3 | Target: 100 Actual: 100 | C: 24.9° A: 28.2° | No | Pending | Admixture: Retarder Batch time: 34 min
21 | 24 Jun 2026 22:20 – 22:50 | Foundation Zone 1 Pile cap | C40 AD Mix 012 | Tkt: TAR-52-22 Trk: TAR-09 | 10m3 | Target: 100 Actual: 105 | C: 24.8° A: 28.0° | No | Pending | Admixture: Retarder Batch time: 26 min
22 | 24 Jun 2026 22:40 – 23:10 | Foundation Zone 1 Pile cap | C40 AD Mix 012 | Tkt: TAR-52-23 Trk: TAR-33 | 6m3 | Target: 100 Actual: 100 | C: 24.7° A: 27.8° | No | NCR opened | Balance load to complete pour item. Total volume pour successful. Admixture: Retarder Batch time: 22 min
TOTALS |  |  |  |  | 2226.0 m³ |  |  |  | 1 / 22 Acc.
QMix Logbook · Lalas Tower 22 · Pours: 22 · Volume: 2226.0 m³ · 26/06/2026 ¦ Generated by Quollnet.com ¦ QMix-logbook