## Slump Test Log
Concrete Slump Test Register / Log
Example field QA/QC slump log
SL-001 | 12/05/2026 09:30 | Level 3 slab – Grid A–D / 1–4 | Metro Concrete / MTC-42 / D-18453 | M32-20-AG20 | 80–120 mm | 24.2 | — | Accepted for placement | C0512-1A, C0512-1B, C0512-1C | — | True slump; no adjustment required.
SL-002 | 12/05/2026 10:45 | Level 3 slab – Grid D–G / 1–4 | Metro Concrete / MTC-51 / D-18461 | M32-20-AG20 | 80–120 mm | 24.8 | — | Accepted for placement | C0512-2A, C0512-2B, C0512-2C | — | Measured slump within specified range.
SL-003 | 12/05/2026 12:10 | Lift core wall – Level 3 | Metro Concrete / MTC-38 / D-18478 | M40-20-PCE | 100–140 mm | 25.6 | 125 mm | Accepted after retest | C0512-3A, C0512-3B, C0512-3C | — | Initial result 95 mm; authorized admixture adjustment followed by remixing and retest.
SL-004 | 13/05/2026 08:55 | Column C14 – Level 4 | South Plant Concrete / SPC-17 / D-22105 | M40-20-PCE | 100–140 mm | 23.7 | — | Accepted for placement | C0513-1A, C0513-1B, C0513-1C | — | True slump; normal concrete appearance.
SL-005 | 13/05/2026 10:20 | Level 4 slab – Grid A–F / 5–9 | South Plant Concrete / SPC-24 / D-22118 | M32-20-AG20 | 80–120 mm | 25.1 | 110 mm | Accepted after retest | C0513-2A, C0512-2B, C0513-2C | — | Initial result 70 mm; load held, retested after authorized adjustment.
SL-006 | 13/05/2026 13:40 | Shear wall SW-04 – Level 4 | South Plant Concrete / SPC-31 / D-22133 | M40-20-PCE | 100–140 mm | 27.3 | 165 mm | Rejected | C0513-3A, C0513-3B, C0513-3C | NCR-026 / RJ-013 | Initial and repeat results outside project requirement; load rejected.
FINAL DISPOSITION KEY |  |  | NOTES |  |  |  |  | RECORD VERIFIED BY
|  |  | • Slump tests conducted in accordance with AS 1012.3.1 / ASTM C143. • Retests performed only after authorized adjustment as per project procedure. • All records to be retained as part of the project quality documentation. |  |  |  |  | Name:
✓ Accepted for placement | [7 empty] | Position:
↻ Accepted after retest | [7 empty] | Signature:
✗ Rejected | [7 empty] | Date: