## Kickoff Checklist
Kick off meeting Checklist
RACI
| Checklist Item |  | Status | Due Date | Responsible (R) | Accountable (A) | Consulted (C) | Informed (I)
1 | Contractual obligations reviewed (LDs, EoT, notices) |  | FALSE |  | PM | PM | QS | Client Rep
2 | Site handing-over date agreed + possession form signed |  | FALSE |  | PM | Client Rep | Site Eng. | Consultant
3 | Programme submission deadline (Clause 14 or equivalent) |  | FALSE |  | Planner | PM | Consultant | Client Rep
4 | Submittal review durations set (e.g., 10 working days) |  | FALSE |  | Doc Control | Consultant | PM | Client Rep
5 | Inspection/test turnaround times agreed |  | FALSE |  | QA/QC | Consultant | Site Eng. | Client Rep
6 | Payment cycle and IPC dates defined |  | FALSE |  | QS | PM | Finance | Client Rep
7 | Change order procedures approved |  | FALSE |  | PM | Client Rep | QS | Consultant
8 | Risk & issue management process active |  | FALSE |  | PMO | PM | Discipline Leads | Client Rep
9 | Document control rules enforced (CDE, naming, revisions) |  | FALSE |  | Doc Control | PM | All Leads | All Stakeholders
10 | MOM circulation window set (24–48h) |  | FALSE |  | PM | PM | Doc Control | All
comments:
Quick governance notes
Single source of truth: Document Control is custodian of the checklist, action log, RACI, review SLAs, and calendars in the CDE.
Approvals: PM signs off on working procedures; Client Rep/Consultant confirm items with contractual impact (dates, programme SLAs, payments).
SLA hints: Minutes 24–48h, Submittal review 7–14 working days, Inspection/test 24–72h per risk/ITP, Change evaluation 2–5 days (project-specific).
Versioning: Use controlled transmittals; version every matrix (RACI, SLA, calendars); log all updates in the action tracker.

## RACI Matrix
Workflow | R | A | C | I
RFIs | Discipline Eng. | PM | Consultant | Client Rep
Submittals | Discipline Eng. | PM | Consultant | Client Rep
Inspections/ITPs | QA/QC | PM | Consultant | Client Rep
Variations/Change Orders | PM | Client Rep | QS | Client Rep
Programme Updates | Planner | PM | Consultant | Client Rep
Delay Notices | PM | PM | Consultant | Client Rep
Valuations/Payments | QS | PM | Finance | Client Rep
QA/QC Records | QA/QC | PM | Consultant | Client Rep
HSE Incidents | HSE Lead | PM | Consultant | Client Rep
Document Control | Doc Control | PM | All Leads | All Stakeholders

## Communication Plan
Channel | Purpose | SLA/Response | Owner
CDE | Single source of truth (documents/transmittals) | As per workflow | Doc Control
Email | Formal instructions/notifications | 48h standard | PM
Weekly Progress Meeting | Status, risks, decisions; action tracker | Weekly | PM
Monthly Report | KPIs, progress, forecast, risks | Monthly | PM
Site Huddle | Daily coordination and safety topics | Daily | Site Eng.