## PPC Application
PROGRESS PAYMENT APPLICATION / CERTIFICATE
COMPANY LETTERHEAD ¦ LOGO / ADDRESS / CONTACT DETAILS
Project | Sample Project (replace)
Employer | Employer name
Contractor | Contractor name
Contract reference | Contract no.
PPC number | 3
Period ending | 2026-10-31
Currency | USD
Original contract value | 1000000
Approved contract adjustment / VOs | 30000
Revised contract value | 1030000
Initial advance payment | 100000
Retention deduction rate | 10%
Retention cap rate | 5%
Retention cap basis | Original
Claims subject to retention? | No
Employer deductions reduce retention base? | No
PAYMENT VALUATION ¦ CUMULATIVE LESS PREVIOUS = THIS PERIOD
Description | Cumulative to date | Previous certified | This period
Executed BOQ work | 420000 | 230000 | 190000
Approved & executed VOs | 30000 | 20000 | 10000
Approved and due contractor claims | 10000 | 0 | 10000
SUBTOTAL: GROSS WORK VALUE | 460000 | 250000 | 210000
Advance paid (memorandum; not added to work) | 100000 | 100000 | 0
Advance recovery (deduction) | 40000 | 20000 | 20000
Retention deduction / balance (deduction) | 45000 | 25000 | 20000
Employer claims / other deductions | 0 | 0 | 0
SUBTOTAL: NET VALUE OF WORK | 375000 | 205000 | 170000
Previously certified net amount (PPC reconciliation) | 205000 | 205000 | 0
CURRENT PPC CERTIFIED VALUE | 170000 | 0 | 170000
Less: cash paid against current PPC | 0 | 0 | 0
CURRENT PPC UNPAID / FOR ACCOUNTS | 170000 | 0 | 170000
Retention base (supporting calculation) | 450000 | 250000 | 200000
Cumulative retention cap (supporting calculation) | 50000 | 50000 | 50000
Current retention (register cross-check) | 20000 | 0 | 20000
Notes: Previous figures refer to previous CERTIFIED amounts, not just bank payments.
Retention claims & employer deductions are contract-dependent switches.
Advance is shown for reference: it is NOT added again to certified work.

## Retention Register
RETENTION SCHEDULE ¦ ATTACH TO PPC
PPC No. | BOQ to date | VO to date | Eligible claims to date | Eligible employer offsets to date | Retention to date
1 | 150000 | 0 | 0 | 0 | 15000
2 | 230000 | 20000 | 0 | 0 | 25000
3 | 420000 | 30000 | 10000 | 0 | 45000
RECONCILIATION WITH CURRENT PPC
Latest cumulative retention | 45000
Previous cumulative retention | 25000
Current-period retention deduction | 20000
Cap amount | 50000
Balance left before cap | 5000

## Instructions
HOW TO USE THE PPC WORKBOOK
1. Replace letterhead, project details and original/revised contract assumptions.
2. Choose cap basis: Original or Revised, based on the signed contract.
3. Decide whether approved claims or employer deductions belong in retention base.
4. Enter current cumulative and previous certified amounts on PPC Application.
5. Enter each PPC as one row in the retention register, with cumulative bases.
6. Reconcile this PPC retention with the register (row 42 / schedule row 30).
7. Accounts section separates certified amount from payments actually received.
8. The sample is illustrative and not a substitute for contract-specific certification.