## Sheet1
| Contractor Name LTD | [6 empty] | date: --/--/--
Variation Order Log
page -- / --
VO No. | Date Detected | Type of Instruction | Notice Due Date | Notice Status | VO Due Date | VO Status | Remarks | Time Impact | Cost Impact
1 | 2025-03-10 | Site Instruction | 2025-03-24 | Submitted | 2025-04-07 | Approved | Foundation depth change | 56 days | Zero
2 | 2025-03-12 | Verbal Instruction | 2025-03-26 | Submitted | 2025-04-09 | Pending | Additional landscaping | 20 dasy | 15000
3 | 2025-03-15 | Revised Drawings | 2025-03-29 | Pending | 2025-04-12 | Pending | Structural steel update | Zero | -50000
4 | 2025-03-18 | Engineer’s comments (Materials) | 2025-04-01 | Submitted | 2025-04-15 | Rejected | Material spec revision | Zero | -12000
5 | 2025-03-20 | Contractor Proposal | 2025-04-03 | Submitted | 2025-04-17 | Approved | Cost-saving initiative | Zero | 28000
Instructions for Use:
VO No.: Unique identifier assigned to each variation for easy tracking.
Date Detected: The date the variation was identified or instructed.
Type of Instruction: Origin of variation (Site Instruction, Verbal, Revised Drawings, Comments, Contractor Proposal, etc.).
Notice Due Date: Deadline for submitting a formal notice to comply with contract terms.
Notice Status: Current status of notice (Pending, Submitted, or Overdue).
VO Due Date: Deadline for submitting the official Variation Order document.
VO Status: Current status of the official VO document (Approved, Pending, Rejected).
Remarks: Brief description or key details regarding the variation.