## Permit Checklist
QUOLLNET — RAMS Pack ¦ Permit Checklist
Identify and track all permits required for this activity. All permits must be approved before work commences.
Permit Type | Required? (Y/N/TBC) | Permit No. / Reference | Issued By | Permit Holder | Valid From / To | Notes
Permit to Excavate / Dig | Y |  | [HSE Officer / Site Manager] | [Superintendent] |  | Required before any ground break; utility scan must precede issue
Permit to Lift (crane / lifting operations) | Y |  | [Lifting Supervisor] | [Crane Operator] |  | Lift plan and rigging sketch to be attached; daily renewal if required
Hot Work Permit (welding, cutting, grinding) | TBC |  | [HSE Officer] | [Supervisor] |  | Required only if on-site cage welding; fire watch; extinguisher at work area
Confined Space Entry Permit | TBC |  | [HSE Officer] | [Entry Supervisor] |  | Verify if any inspection or entry into bore or similar space is required
Electrical Isolation Permit | TBC |  | [Authorised Electrician] |  |  | Near overhead or underground electrical services
Working Near Water / Drainage | TBC |  | [HSE Officer] |  |  | If dewatering or working near watercourses — verify local regulatory requirement
Environmental / Noise Permit | TBC |  | [Environmental Manager] |  |  | If required by local authority or project environment plan
[Add permit as required]