## Risk Register
QUOLLNET — RAMS Pack ¦ Risk Register
Complete one row per hazard per work step. Risk Rating = Likelihood × Severity. Verify all thresholds against company HSE procedure or project requirements.
# | Step No. | Work Step | Hazard | Possible Consequence | Persons at Risk | Initial Likelihood | Initial Severity | Initial Risk Rating | Control Measures | Residual Likelihood | Residual Severity | Residual Risk Rating | Additional Action Required | Responsible Person | Target Date | Status | Permit / ITP / WIR Ref.
1 | 1 | Site Establishment & Setting Out | Underground utility strike during setting out / trial pitting | Electrocution; gas release; flooding; asset damage | Workers; site personnel | 4 | 5 | 20 | Review updated utility drawings; CAT/Genny scan; trial pits; Permit to Dig signed before any ground break; minimum clearance distances from live services; spotter during initial work; utility provider notification | 2 | 4 | 8 |  | [HSE Officer] |  | Open | [Permit-to-Dig P-001; ITP-01]
2 | 2 | Rig Mobilisation & Platform Setup | Rig overturning on weak platform; crane tip-over during lift | Fatal crush injury; asset loss; third-party damage | Rig operator; crew; public | 3 | 5 | 15 | Platform certified by geotechnical engineer; bearing capacity verified; rig mats installed; daily platform inspection after rain; exclusion zone ≥ rig radius + 3m; banksman always present; rig operator certification current; lift plan reviewed and approved | 1 | 5 | 5 |  | [Superintendent] |  | Open | [Platform Certificate; Permit-to-Lift P-002; ITP-02]
3 | 3 | Dry Drilling | Entanglement with rotating auger / kelly bar; ejected debris | Amputation; crush; eye injury | Rig operator; assistants nearby | 3 | 5 | 15 | No-go zone around rig during rotation; guarding in place; lockout during tool changes; only competent trained personnel within 5m; snug clothing; PPE — hard hat, safety glasses, gloves; toolbox talk before start; supervisor present | 2 | 4 | 8 |  | [Rig Operator; Superintendent] |  | Open | [ITP-03]
4 | 3 | Dry Drilling | Fall into open borehole | Fatal fall; head/spinal injury | Workers; visitors | 3 | 5 | 15 | All open boreholes covered immediately with rated steel plates or guarded with rigid barriers; never leave uncovered and unattended; covers marked and secured; nightly site inspection; supervisor sign-off before breaks | 1 | 5 | 5 |  | [Superintendent; HSE Officer] |  | Open | [HSE Plan Sec. 4]
5 | 4 | Reinforcement Cage Lifting | Dropped load during cage lift; cage swing striking personnel | Fatal struck-by; crush; fracture | Lifting crew; nearby workers | 3 | 5 | 15 | Lift plan approved; crane and all lifting gear certified and inspected; certified slings and shackles — SWL verified; tag lines used; wind limit per lift plan (typically ≤ 10 m/s — Verify); no personnel under suspended load; exclusion zone during lift; banksman controls all movements; pre-lift meeting completed | 1 | 5 | 5 |  | [Lifting Supervisor; Crane Operator] |  | Open | [Permit-to-Lift P-002; Lift Plan LP-001; ITP-05]
6 | 5 | Concrete Placement (Tremie) | Pump line failure / whip; concrete splatter | Impact injury; alkali burns to skin/eyes | Concrete crew; nearby workers | 3 | 3 | 9 | Pressure test pump lines; whip checks (safety cables) on all couplings; safety pins / clamps at joints; all personnel clear of line during pumping; face shield and chemical-resistant gloves for concrete crew; eyewash station on site | 2 | 2 | 4 |  | [Concrete Supervisor] |  | Open | [ITP-06]
7 | 5 | Concrete Placement (Tremie) | Cement / concrete chemical skin and eye exposure | Dermatitis; severe alkali burns | Concrete crew; steel fixers | 4 | 2 | 8 | Avoid direct skin contact; alkali-resistant gloves; safety glasses; long-sleeve clothing; welfare facilities with soap and water adjacent to work area; eyewash station; SDS for all admixtures available on site | 2 | 2 | 4 |  | [HSE Officer; Concrete Supervisor] |  | Open | [SDS — Concrete]
8 | 6 | Casing Extraction | Sudden casing drop or lurch injuring personnel | Crush; fracture; fatality | Rig crew; nearby personnel | 3 | 5 | 15 | Controlled extraction speed; exclusion zone maintained; no manual handling of casing during extraction; plant operator trained on casing extraction procedure; adequate concrete head maintained; supervisor monitoring | 1 | 5 | 5 |  | [Superintendent; Rig Operator] |  | Open | [ITP-07]
9 | 9 | All Steps | Noise-induced hearing loss from drilling / piling operations | Permanent hearing damage | All site personnel | 4 | 3 | 12 | Mandatory hearing protection in all noisy zones; ear defenders EN 352 or equiv.; maintained tooling reduces noise output; work hour restrictions near sensitive receptors; noise monitoring if required by permit | 2 | 2 | 4 |  | [HSE Officer] |  | Open | [HSE Plan; Environmental Permit if applicable]
10 | 13 | Demobilisation | Vehicle / plant movement striking personnel during demob | Struck-by injury; fatality | All site personnel; public | 3 | 4 | 12 | Traffic management plan active during demob; banksman controlling all plant movements; hi-vis worn by all; pedestrian exclusion from vehicle routes; speed limit ≤ 10 km/h on site | 2 | 3 | 6 |  | [Superintendent; HSE Officer] |  | Open | [Traffic Management Plan TMP-001]