## Construction Delay Log
Company Name
| Company Address | Construction Delay Log
Email
Telephone
Date | Activity | Delay Cause | Responsible Party | Impact (Days) | Critical Path Affected | Corrective Action | EOT Claimed | EOT ID
2025-04-01 | Foundation Pouring | Heavy Rain | Weather | 2 | Yes | Rescheduled to 04/04 | No
2025-04-03 | Steel Delivery | Supplier Delay | Supplier | 3 | Yes | Expedited alternate supplier | Yes
2025-04-07 | Crane Installation | Permit Issue | Client | 1 | No | Permit obtained on 04/06 | No
How to Use the Construction Delay Log Template: |  |  |  |  | 3. Always issue a formal delay notice immediately upon identifying a delay to preserv
1. Record every delay event as soon as it occurs to avoid loss of information. |  |  |  |  | your contractual rights for an EOT claim.
2. Fill in the following columns for each event: |  |  |  |  | 4. Use the EOT ID to refer to more detailed EOT documentation, including justification
- Date: When the delay happened or was first identified. |  |  |  |  | and supporting evidence.
- Activity: The task or part of the project affected. |  |  |  |  | 5. Review the log weekly during project meetings and use it as the foundation for EOT
- Delay Cause: Weather, late delivery, permit issues, etc. |  |  |  |  | submissions and client communications.
- Responsible Party: Identify if the delay is due to the contractor, client, third-party, or uncontrollable events.
- Impact (Days): Estimate the number of days this delay affects the schedule.
- Critical Path Affected: Mark "Yes" if the delay impacts the project finish date.
- Corrective Action: Mention any mitigation steps taken.
- EOT Claimed: Indicate whether an Extension of Time (EOT) was claimed.
- EOT ID: Cross-reference the delay to its related EOT log entry.