## Sheet1
Join Condition Server (Site Handing Over)
Project Name: | [5 empty] | Participants | 1 |  |  | 2
Project Id: | [6 empty] | 3 |  |  | 4
Date of Survey
Log ID | Area / Phase | Grid | Chainage | Lat | Lon | Pre-Exist? | Type | Sev. | Description | Photos | Resp. | Action | Target Date | Status
LOG-2025-001 | Phase 1 – North Yard | C4 | CH 0+120 | 33.8938 | 35.5018 | Y | Crack | Med | Hairline longitudinal crack ~4 m near gate | PHO-2025-010, PHO-2025-011 | Employer | Cold patch repair; re-inspect | 2025-11-08 | Open
LOG-2025-002 | Phase 1 – North Yard | C5 | CH 0+121 | 33.8938 | 35.5018 | Y | Crack | Med | Hairline longitudinal crack ~4 m near gate | PHO-2025-010, PHO-2025-012 | Employer | Cold patch repair; re-inspect | 2025-11-09 | Open
LOG-2025-003 | Phase 1 – North Yard | C6 | CH 0+122 | 33.8938 | 35.5018 | Y | Crack | Med | Hairline longitudinal crack ~4 m near gate | PHO-2025-010, PHO-2025-013 | Employer | Cold patch repair; re-inspect | 2025-11-10 | Open
What it is:
This is a Joint Condition Survey (Site Handover) log—a snapshot of the site’s baseline condition at the moment possession is granted to the contractor. Each row records one observation (location + defect/feature), with photo references and agreed responsibilities. It protects both parties by fixing what was pre-existing before works start and by listing any immediate actions.
How to fill it (brief):
Enter the Log ID (unique), then the Area/Phase, Grid, and Chainage to pinpoint the location. Add Lat/Lon if available. Mark Pre-Exist? as Y only if the condition existed before possession. Choose a Type (e.g., Crack) and Severity (Low/Med/High), then write a concise Description (extent/size/nearby reference). List Photos by ID that show the condition. Assign Resp. (Employer/Contractor/Authority) and a clear Action (e.g., “Cold patch repair; re-inspect”). Set a realistic Target Date and track Status (Open/Monitor/Closed). At the top, complete Project Name/ID, Date of Survey, and the Participants (names/roles) to confirm joint attendance.