## Slump Test Report
| Quol LDA |  | CONCRETE SLUMP TEST REPORT |  |  |  | R No. | QNL-QC-ST-2026-0512
| Lisbon, Portugal | [5 empty] | Date | 12 May 2026
https://quollnet.com |  |  | Field QA/QC Record |  |  |  | Page | 1 of 1
1 | 🏢 PROJECT & POUR DETAILS
Project Name |  | Harbourview Commercial Tower |  |  | Pour Location |  | Level 3 – Core Zone
Structural Element |  | Lift Core Walls |  |  | Contractor |  | QS Constructions Pty Ltd
Consultant / Engineer |  | Quollnet Engineering |  |  | Work Package / Reference |  | WP-STR-03
2 | 🚚 SUPPLY & DELIVERY TRACEABILITY
Supplier |  | Metro Concrete |  |  | Plant |  | Southyard Batching Plant
Truck No. |  | MTC-42 |  |  | Delivery Ticket No. |  | D-2026-18453
Mix Reference |  | M30-20-AG20 |  |  | Concrete Grade / Designation |  | 32 MPa
Max Aggregate Size |  | 20 mm |  |  | Admixture / Workability System |  | PCE Based
3 | ⏱ TIMING & CONDITIONS
Batch Time |  | Arrival Time |  | Sampling Time | Test Time |  | Concrete Temp. |  | Ambient Temp.
08:45 |  | 09:20 |  | 09:25 | 09:30 |  | 24.2 °C |  | 22.1 °C
4 | 🎯 SLUMP REQUIREMENT |  |  |  | 5 | 📋 INITIAL TEST RESULT
Specified Slump (Range) |  | 80 – 120 mm |  |  | Measured Slump | 95 mm |  | Slump Sketch (mm): 95
Basis |  | Project Specification Section 03 30 00 |  |  | Slump Type | ☑ True ☐ Shear
Requirement Type |  | ☐ Target ☑ Range ☐ Maximum ☐ Class |  |  |  | ☐ Collapse ☐ Zero
Test Standard |  | BS EN 12350-2 / ASTM C143 |  |  | Sampling / Test Point |  | Truck discharge
6 | 💧 ADJUSTMENT / RETEST (If applicable)
Adjustment |  | ☑ No Adjustment |  | ☐ Water Added ____ L |  | ☐ Admixture Added ____ L
Authorized by |  | N/A |  |  | Authorization Ref:
Retest Time |  | N/A |  | Retest Slump | N/A |  | Slump Type |  | N/A
Note: Initial test result above is retained. Retest recorded for information only.
7 | 🧊 SAMPLE IDS (From Same Sample / Load)
Cube IDs / size |  | C0512-1A, C0512-1B, C0512-1C |  |  | Cyl IDs / size |  | CY0512-1A, CY0512-1B
Sample Taken By |  | Jordan Lee (QS Constructions) |  |  | Curing Location |  | On Site Curing Area
8 | ⚖ FINAL LOAD DISPOSITION (Field Record)
☑ Accepted for Placement |  |  | ☐ Held (Do Not Place) |  | ☐ Retested (See Section 6) |  | ☐ Adjusted (See Section 6) |  | ☐ Rejected (Do Not Place)
Load / Pour Decision Notes |  |  | Slump within specified range. Proceed with placement.
9 | 💬 REMARKS / OBSERVATIONS
Workability good. No segregation or bleeding observed. Placement started at 09:45.
10 | 👥 SIGNATORIES (Field Record)
Tested By |  |  |  | Witnessed By |  |  | Disposition Recorded By (Load Decision By)
Name |  | Jordan Lee |  | Name | Michael Tan |  | Name | Daniel Harris
Company |  | QS Constructions |  | Company | Quollnet Engineering |  | Company | QS Constructions
Signature |  |  |  | Signature |  |  | Signature
Date / Time |  | 12/05/2026 09:35 |  | Date / Time | 12/05/2026 09:40 |  | Date / Time | 12/05/2026 09:48
Quoll Unipessoal LDA |  |  |  |  | Form No.: QNL-FRM-QC-013
Avenida Engenheiro A. e Oliveira, nº 3, R/C,1900-221 Lisboa |  |  |  |  | Revision: 1.0 ¦ Effective: 01/01/2026