## Sheet1
Quollnet.com
Construction Tender Progress Log
Tender ID | Project | ITB Recvd | Decision to Bid | Estimation | Financial | Technical | Dates & State
T-001 | Riverside Apartments 2B + G + 22 Typicals + Roof | 2025-06-01 | Go (2025-06-05) | QS: Completed WBS: Completed RFQ: In Progress BOQ: Not Started | Bond Issued: Completed Cashflow: In Progress Cost Model: Not Started | Doc Review/Queries: Completed Method Statement: Completed HSE Plan: In Progress Programme: Not Started Risk Register: Not Started | Due: 2025-06-12 Submitted: – State: In Progress
T-002 | City Hall Renovation G + 2 Typicals + Basement | 2025-05-15 | Under Review (2025-05-20) | QS: In Progress WBS: Not Started RFQ: Not Started BOQ: Not Started | Bond Issued: Not Started Cashflow: Not Started Cost Model: Not Started | Doc Review/Queries: Not Started Method Statement: Not Started HSE Plan: Not Started Programme: Not Started Risk Register: Not Started | Due: 2025-05-20 Submitted: – State: Pending Review
T-003 | Midtown Office Tower 3B + G + 20 Typicals + Roof | 2025-04-20 | No-Go (2025-04-25) | QS: In Progress WBS: Not Started RFQ: Not Started BOQ: Not Started | Bond Issued: Not Started Cashflow: Not Started Cost Model: Not Started | Doc Review/Queries: Not Started Method Statement: Not Started HSE Plan: Not Started Programme: Not Started Risk Register: Not Started | Due: – Submitted: – State: Closed
This sheet records every tender’s progress across three parallel streams—Estimation, Financial, Technical—plus key dates and overall state.
Tender ID: unique code
Project: name and brief description
ITB Recvd & Decision to Bid: dates and Go/No-Go
Estimation / Financial / Technical: list sub-tasks with status (Completed / In Progress / Not Started)
Dates & State: next due date, submission date, and overall status
Update immediately when any milestone changes; use line-breaks (Alt+Enter) in cells and color-code overdue (red) or imminent (amber) items.