## Cash Flow
CashFlowPot
Sample Project · LDEEREO
Sample Construction Cash Flow
Worked example showing Work activities, Scheduled Cost, client contract terms, an independent inflow curve, an LC and a revolving overdraft.
Contract & Financing Assumptions
| Contract Value | 5800000 |  |  | Client Advance |  |  | 10% |  | Client Retention |  |  | 10%
| Retention Released at Completion | 50% |  |  | Defects Liability Period |  |  | 6 |  | Client Payment Delay |  |  | 2
| Billing Deferral | 20% |  |  | Financing Rate per Period |  |  | 0.5% |  | Work Duration |  |  | 21
| Financial Horizon | 30
Key Metrics
| Contract Value |  |  |  | Direct Cost |  |  |  |  | Financing Cost
| Total Forecast Cost |  |  |  | Forecast Margin Before Financing |  |  |  |  | Forecast Margin After Financing
| Closing Cash Balance |  |  |  | Peak Funding Requirement |  |  | -680995.27 |  | Peak Funding Period |  |  | 10
| Work Duration |  |  |  | Financial Horizon |  |  |  |  | Cash after debt settlement
Charts
Cashflow Schedule |  | Duration | Start | Pre Work | Estimated Cost | Flow | Group 1 |  |  |  | Group 2 |  |  |  | Group 3 |  |  |  | Group 4 |  |  |  | Group 5 |  |  |  | Group 6 |  |  |  | Group 7 |  |  |  | Group 8 |  | Total / Closing
No. | Activity | [5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
1 | Testing & handover | 3 | 19 | 0 | 200000 | Work | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66666.67 | 66666.67 | 66666.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Outflow | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66666.67 | 66666.67 | 66666.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Preliminaries | 3 | 1 | 0 | 300000 | Work | 100000 | 100000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Outflow | 100000 | 100000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Substructure | 5 | 2 | 1 | 750000 | Work | 0 | 0 | 22967.38 | 131541.78 | 341469.26 | 210493.09 | 43528.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Outflow | 0 | 33750 | 12632.06 | 79789.41 | 231254.46 | 231142.74 | 104433.32 | 21680.98 | 18442.03 | 0 | 0 | 0 | 0 | 0 | 16875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Superstructure | 9 | 5 | 1 | 1400000 | Work | 0 | 0 | 0 | 0 | 0 | 19353.22 | 55593.44 | 142958.61 | 290946.51 | 382296.44 | 290946.51 | 142958.61 | 55593.44 | 19353.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Outflow | 0 | 0 | 0 | 0 | 24500 | 12579.59 | 41029.68 | 107844.92 | 227746.75 | 328445.31 | 298771.93 | 183556.17 | 85269.88 | 33017.31 | 7374.8 | 25363.64 | 0 | 0 | 0 | 0 | 0 | 24500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | MEP | 8 | 9 | 1 | 900000 | Work | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | 90000 | 120000 | 150000 | 170000 | 150000 | 100000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Outflow | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 81000 | 6000 | 9000 | 12000 | 101400 | 107720 | 118680 | 129520 | 116880 | 79200 | 48960 | 49140 | 0 | 0 | 0 | 0 | 0 | 40500 | 0 | 0 | 0 | 0
6 | Facade & finishes | 9 | 11 | 1 | 1050000 | Work | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24968.53 | 69074.58 | 161476.34 | 268757.7 | 266417.98 | 158067.63 | 67612.82 | 25065.58 | 8558.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Outflow | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78750 | 6242.13 | 17268.65 | 52353.98 | 103341.45 | 152402.09 | 187897.77 | 177034.76 | 114109.02 | 53561.98 | 20145.02 | 7116.11 | 40402.06 | 0 | 0 | 0 | 0 | 0 | 39375 | 0
7 | Major Equipment Purchase | 6 | 7 | 0 | 700000 | Scheduled cost | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Outflow | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 250000 | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PROJECT CASHFLOW | [6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
1 | Project inflow Client PPC receipts | [5 empty] | 580000 | 0 | 15317.68 | 28647.42 | 45488.62 | 71023.65 | 109071.91 | 163818.08 | 238085.14 | 329823.5 | 427603.77 | 509100.25 | 548285.75 | 530485.38 | 462745.24 | 368534.39 | 272760.24 | 191123.1 | 128865.07 | 84645.44 | 54584.77 | 34639.02 | 21522.18 | 293829.42 | 0 | 0 | 0 | 0 | 0 | 290000
2 | Project cost Work + scheduled costs | [5 empty] | 100000 | 133750 | 112632.06 | 79789.41 | 255754.46 | 243722.34 | 295463.01 | 129525.91 | 327188.77 | 584445.31 | 386521.93 | 501798.3 | 203938.53 | 193091.29 | 246271.25 | 307285.72 | 304777.77 | 256234.76 | 229735.68 | 169368.64 | 86811.68 | 31616.11 | 40402.06 | 0 | 0 | 40500 | 0 | 0 | 39375 | 0
FACILITIES | [6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
LC MEP | Draw | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 0 | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Repayment | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82455.88 | 106900.94 | 60643.18 | 137071.44 | 112928.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Interest & fees | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 2000 | 1340.35 | 485.15 | 2000 | 903.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Outstanding balance | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 167544.12 | 60643.18 | 250000 | 112928.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project Overdraft | Draw | [5 empty] | 0 | 0 | 0 | 0 | 14972.21 | 172878.36 | 188645.31 | 0 | 0 | 341417.52 | 73596.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5013.59 | 32287.07 | 0 | 19296.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Repayment | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29774.22 | 151735.71 | 0 | 0 | 188853.62 | 200222.03 | 220911.01 | 13.09 | 0 | 0 | 0 | 0 | 0 | 0 | 2575.3 | 0 | 54021.95 | 0 | 0 | 0 | 0 | 0 | 0
| Interest & fees | [5 empty] | 2500 | 0 | 0 | 0 | 0 | 179.67 | 2254.21 | 4517.95 | 4160.66 | 2339.83 | 6436.84 | 7320 | 5053.75 | 2651.09 | 0.16 | 0 | 0 | 0 | 0 | 0 | 60.16 | 447.61 | 416.7 | 648.26 | 0 | 0 | 0 | 0 | 0 | 0
| Outstanding balance | [5 empty] | 0 | 0 | 0 | 0 | 14972.21 | 187850.57 | 376495.87 | 346721.65 | 194985.94 | 536403.46 | 609999.76 | 421146.13 | 220924.1 | 13.09 | 0 | 0 | 0 | 0 | 0 | 5013.59 | 37300.66 | 34725.36 | 54021.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CASH POSITION | [6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
5 | Total inflow
6 | Total outflow
7 | Net cash flow
8 | Closing cash balance
Reconciliation & Notes | bar: 1 to 7
| CashFlowPot Reference Closing Balance |  |  | 449284.21
Workbook Closing Balance
Difference
Status
All monetary amounts are shown in the project's reporting currency. Timing is expressed in model periods. Facility rows use the calculated financing result; interest and fees are combined for reporting.