## Backcharge Log
|  | Backcharge Log | [5 empty] | Project Name:
|  | Template for Subcontractor Costs and IPC Deductions | [5 empty] | Project No.:
ⓘ Administrative and commercial control record used to track Subcontractor backcharges from the initial notice and cure period through cost assessment, approval, dispute, IPC deduction, remaining balance, reversal, and closure. Entry in the log does not by itself establish liability, approve the cost, or create a contractual right to deduct. | [7 empty] | Prepared By:
Date:
no. | Notice No. | Project | Subcontractor | Trade | Date Raised | Issue / Location | Cure Deadline | Estimated Amount | Approved Amount | Disputed Amount | IPC No. | Current Deduction | Total Deducted | Remaining Balance | Status
1 | BCN-001 | Riverside Tower | Alpha Formwork Ltd. | Formwork | 06 May 2025 | Delay in formwork stripping on Level 12 - Grid B1-B4 | 20 May 2025 | 18750 | - | - | IPC-007 | 0 | 0 | - | Cure Period Open
2 | BCN-002 | Riverside Tower | Summit Concrete Pty Ltd | Concrete | 15 Apr 2025 | Concrete cold joint on Level 8 - Pour 3 (Area C) | 29 Apr 2025 | 24980 | 19980 | 0 | IPC-008 | 4000 | 10000 | 9980 | Deduction in Progress
3 | BCN-003 | Riverside Tower | Core Electrical Services | Electrical | 28 Apr 2025 | Missing cable supports in Level 10 plant room | 12 May 2025 | 8650 | 0 | 8650 | IPC-009 | 0 | 0 | 0 | Disputed
Recommended Status Options: Draft · Notice Issued · Cure Period Open · Approved · Disputed · Deduction in Progress · Fully Deducted · Reversed · Closed
Formula Note: Remaining Balance = Approved Amount − Total Deducted to Date