## RACI_Matrix
RACI Matrix (Construction)
Legend: R=Responsible (does the work) ¦ A=Accountable (final sign-off) ¦ C=Consulted ¦ I=Informed
Enter only R / A / C / I in the matrix cells. Typical practice: one 'A' per activity.
Activity / Process | Client/Owner | Engineer/Consultant | PMC (if any) | Contractor - PM | Contractor - CM/Site Mgr | Technical Manager | QA/QC Manager | HSE Manager | Planning/Scheduler | Commercial/QS | Procurement | Document Control | Site/Section Engineer | Foreman | Subcontractor
Approve Project Org Chart / Key Personnel
Method Statement (prepare / review / approve)
ITP (Inspection & Test Plan) (prepare / review / approve)
Material Submittal (MIR) (submit / review / approve)
Work Inspection Request (WIR) / Hold & Witness Points
RFI (Request for Information)
Site Instruction / Field Change
NCR (Non-Conformance Report) (issue / respond / close)
Corrective Action / Root Cause Analysis
HSE Induction / Toolbox Talk
Permit to Work (hot work, confined space, etc.)
Daily Progress Reporting
Baseline Program + Lookahead (2–6 weeks)
Variation / Change Order (initiate / price / approve)
Interim Payment Request / Monthly Valuation
Subcontractor Procurement & Award
Material Procurement & Delivery (logistics)
Testing & Commissioning Plan
As-Built Drawings & O&M Manuals
Handover / Taking-Over / Punch List Closure
Optional quick key:
R | Responsible
A | Accountable
C | Consulted
I | Informed
1) Review Roles_List and adjust roles to match your project and contract setup.
2) Review Activities_List and keep only the processes you actively manage and report.
3) In RACI_Matrix, use only: R (Responsible), A (Accountable), C (Consulted), I (Informed).
4) Best practice: assign one A per activity (single-point accountability).
5) Org chart = reporting lines. RACI = responsibility for processes/approvals. Use both together.
6) If submitting to a client, align responsibilities with contract terms (approvals, hold points, key personnel).

## Roles_List
Roles (edit as needed)
Role | Notes
Client/Owner
Engineer/Consultant
PMC (if any)
Contractor - PM
Contractor - CM/Site Mgr
Technical Manager
QA/QC Manager
HSE Manager
Planning/Scheduler
Commercial/QS
Procurement
Document Control
Site/Section Engineer
Foreman
Subcontractor

## Activities_List
Activities / Processes (edit as needed)
Activity | Notes
Approve Project Org Chart / Key Personnel
Method Statement (prepare / review / approve)
ITP (Inspection & Test Plan) (prepare / review / approve)
Material Submittal (MIR) (submit / review / approve)
Work Inspection Request (WIR) / Hold & Witness Points
RFI (Request for Information)
Site Instruction / Field Change
NCR (Non-Conformance Report) (issue / respond / close)
Corrective Action / Root Cause Analysis
HSE Induction / Toolbox Talk
Permit to Work (hot work, confined space, etc.)
Daily Progress Reporting
Baseline Program + Lookahead (2–6 weeks)
Variation / Change Order (initiate / price / approve)
Interim Payment Request / Monthly Valuation
Subcontractor Procurement & Award
Material Procurement & Delivery (logistics)
Testing & Commissioning Plan
As-Built Drawings & O&M Manuals
Handover / Taking-Over / Punch List Closure

## Instructions
How to use this RACI template
1) Review Roles_List and adjust roles to match your project and contract setup.
2) Review Activities_List and keep only the processes you actively manage and report.
3) In RACI_Matrix, use only: R (Responsible), A (Accountable), C (Consulted), I (Informed).
4) Best practice: assign one A per activity (single-point accountability).
5) Org chart = reporting lines. RACI = responsibility for processes/approvals. Use both together.
6) If submitting to a client, align responsibilities with contract terms (approvals, hold points, key personnel).