## Sheet1
Quollnet.com
Construction Tender Register & Bid Tracker
Tender ID | Project | Client | Consultant / Tender Manager | Invitation Recv’d | Decision to Bid | Due Date | Result | Contract Value* | Failure Reason | Operations Feedback
T-001 | Riverside Apartments;2B + G + 22 Typicals + Roof | GreenBuild Co. jane@gb.com +961 71 123 456 | A & A john@s-a.com +961 71 654 321 | 2025-06-01 | Yes (05/06/2025) | 2025-06-15 | Won | 10250000 | – | –
T-002 | City Hall Renovation;G + 2 Typicals + Basement | Metro tendt@metro.gov +961 71 234 567 | BuildRight Ltd. mary@br.com +961 71 765 432 | 2025-05-15 | Yes (20/05/2025) | 2025-06-01 | Lost | – | Margin too low | Underestimated material costs
T-003 | Midtown Office Tower;3B + G + 20 Typicals + Roof | Skyline Dev. lucia@sky.com +961 71 345 678 | CivTech omar@ct.com +961 71 876 543 | 2025-04-20 | No (25/04/2025) | – | Closed | – | Out of strategic scope | Refine no-bid criteria
This Construction Tender Register Log captures each bid from invitation to outcome. For every Tender ID, record the Invitation Received date, your Go/No-Go decision (with date), next Due Date, and final Result. Enter the Contract Value only for won tenders, and use the Failure Reason and Operations Feedback fields to note why bids were lost. The Client and Consultant/Tender Manager columns include company name, email, and phone (use Alt + Enter for line breaks). Update this log at each milestone to keep your bidding pipeline transparent and drive continuous improvement.