## daily construction delay report
| Company Name | Daily Site Delay Report
Company Address
Email
Daily Site Delay Report Date: |  |  | Project Name:
| 2025-04-16 |  |  | Downtown Tower Expansion
Site Location: |  |  | Project Number:
| Plot 24, Marina District |  |  | A-622
Weather Conditions:
Cloudy, light rain in the morning
Delay Incident Time
: 08:30 AM
Affected Activity:
Steel Frame Erection
Cause of Delay:
Crane malfunction
Impact on Schedule:
Loss of 1 full working day
Responsibility:
Main Contractor / Crane Maintenance
Corrective Action Taken:
Requested crane technician, work resumed at 1:00 PM
Remarks (Safety, Environment, others):
No safety incidents. Temporary rescheduling of adjacent tasks initiated.
This delay report is a subsection of the broader Daily Site Report and should be completed whenever an incident impacts the project schedule. To ensure proper tracking and escalation, a summary of all recorded delays should be compiled and included in periodic reports, such as weekly, bi-weekly, or monthly progress reports. This provides project stakeholders with a clear overview of disruptions, their causes, and any associated Extension of Time (EOT) claims, supporting better decision-making and contractual compliance.