## delay analysis method selector
Delay Analysis Method Selector Tool
This Excel tool helps you choose the most appropriate delay analysis method based on your project’s conditions, data availability, and complexity.
In the Score column, user the dropdown to rate each question from 1 to 5
1 = Strongly Disagree
5 = Strongly Agree
Item | Criteria / Question | Score
A | Is your project short (<6 months), simple, and stable (minimal changes)? | 2
B | Do you need hypothetical modeling for early-stage or prospective claims? | 3
C | Is your as-built data accurate, detailed, and reliable? | 4
D | Is your original approved baseline schedule complete and available? | 1
E | Are all project activities clearly defined, realistic, and logically linked? | 1
F | Are there multiple overlapping (concurrent) delays requiring precise allocation? | 4
G | Do you need continuous, real-time evaluation of delays during project execution? | 1
H | Is your project highly complex with frequently shifting critical paths? | 2
I | Do contractual/legal standards (FIDIC, NEC, SCL Protocol) strongly apply? | 1
J | Is your available schedule or delay event data limited or incomplete? | 3
K | Does your schedule have a large number of activities (>200)? | 5
L | Are your schedule updates performed regularly (e.g., monthly or more frequent)? | 1
| Total Score | 28
Recommended Method(s)
Use Collapsed As-Built or Windows Analysis
Tutorial: How to Use the Delay Analysis Method Selector Tool
This Excel tool helps you choose the most appropriate delay analysis method based on your project’s conditions, data availability, and complexity.
🔹 Step 1: Score Each Statement
In the "Score (1–5)" column, use the dropdown to rate each question:
1 = Strongly Disagree
5 = Strongly Agree
🔹 Step 2: View the Total Score
Your total score is calculated automatically in the "Total Score" row at the bottom.
🔹 Step 3: Get a Recommendation
Based on your total score, the tool will recommend the most suitable delay analysis method(s), such as:
As-Planned vs. As-Built
Impacted As-Planned
Time Impact Analysis (TIA)
Windows Analysis
Collapsed As-Built
🔹 Example:
If your total score is 28, the tool may recommend:
“Use Collapsed As-Built or Windows Analysis”
🛠 Tips:
If you're unsure how to score a question, consult your project records or speak with your planning team. You can update the inputs as your project evolves.