## ITP - Concrete Works
| Quollnet.com |  | Project: |  | Contractor: |  |  |  |  | I.T.P
|  |  | XXX XXXX XXXXX - XXXX |  |  | ACME LLC
| contact@quollnet.com |  |  |  |  | contact@acme.com |  |  |  | Inspection test plan
Dates: |  |  | Contract Numnber / Trade: |  | Parties: |  |  |  | ITP Number . Revision
| Date Issued: |  | Civil/Strcture/Concrete Works |  | Prepared By: |  |  |  | 701-ITP-03-31 - Rev 2
| Date Approved: |  | Contract 701-25 |  | On Behalf of:
Legend: H = Hold (stop until release) · W = Witness (notify) · S = Surveillance/Review · C = Contractor · S/C = Subcontractor · E = Engineer/Client Rep · TPI = Third-Party Inspector.
Seq | Activity/Step | Inspectionn Test | References | Acceptance Criteria | Method Procedure | Frequency Sampling | Records | Resp | Pt | DM (min) | Remarks
Submitted By: |  |  | Reviewed by: |  | Approved by: |  |  |  | Comments:
date: |  |  | date: |  | date: |  |  |  | date:
How to use this ITP template Start by deciding the scope of the template (e.g., “Concrete—Slab on Grade,” “Structural Steel—Bolting,” “Fire Pump Pressure Test”). Then work row-by-row: 1 - Fill the header (project, contract, revision, date, prepared/reviewed/approved). 2 - List the activity/step in sequence and choose the Inspection/Test method (e.g., “Visual & Measure,” “Lab Test,” “Document Review”). 3 - In References, cite the controlling specs/standards and any approved submittals using clear tags so they’re easy to audit later: [MS: Method Statement ID Approved], [SD: Shop Drawing No Rev Approved], [MD: Mix Design ID Approved], [WPS/PQR: IDs Approved], [MAT: Product Data Approved], [CERT: Calibration/Mill Cert]. 4 - Write Acceptance Criteria as measurable statements (numbers/tolerances where possible). Aim for “pass/fail,” not “looks OK.” 5 - Under Method/Procedure, give the test or inspection reference (e.g., ASTM/EN procedure, checklist name). 6 - Set Frequency/Sampling (every truck, each lot, first of kind, 10% spot check, etc.). 7 - Select Resp (who does it: C, S/C, E, TPI) and Pt (H = Hold, W = Witness, S = Surveillance/Review). 8 - For H or W, enter Notice (h)—the minimum advance notice to the authority (typical ranges: 24–72 hours). 9 - List Records you’ll file (checklists, test reports, photos, batch tickets, calibration certs). 10 - Use Remarks for practical notes (e.g., “No pour without signed ITR,” “Provide curing method in TBT”). Keep the legend on the sheet so everyone reads Pt/Resp/notice the same way. If a step doesn’t need a checklist, leave it blank; if it does, add the form name so your team can find it quickly. |  |  |  |  | How an ITP works (quick primer) An Inspection & Test Plan is the roadmap for quality: it tells the team what to check, when, how, against which acceptance criteria, and who signs. The ITP sits under your project’s QMS and links everyday construction to the contract/specs. Approvals first: Many steps depend on prior submittal approvals (method statements, shop/coordination drawings, mix designs, WPS/PQR, product data). List those approvals in References so the ITP shows its prerequisites. * Gates that control work: * Hold (H): work must not proceed past this step until the Engineer/authority releases it. * Witness (W): you notify by the stated notice hours; if they attend, they sign; if not, the contract usually allows work to proceed after the grace period—keep proof of notice. * Surveillance/Review (S): routine checks; no gate, but records matter. * Evidence + traceability: Each step produces records (checklists, test reports, photos, tickets, calibrations). These become your proof for acceptance, payment, and audits. * Nonconformance path: If criteria aren’t met, raise an NCR, contain/correct, and re-inspect/re-test as required before closing out the step. Use the empty template to build trade-specific ITPs, then compare with the concrete works example to calibrate your acceptance criteria, hold/witness points, notification windows, and records. The goal is a template that a site engineer can print or open on a tablet and execute without guessing what “good” looks like.