## Sheet1
Quollnet.com
Non-Conformance Report - LOG
NCR ID | NCR Date | NCR Status | Work Package | Location + Requirement | Quality Control References | People Control | Response / Disposition | Verification / Closure | Financial / Contractual
107-NCR-01 | 2026-01-02 | Closed | Package: Structure Trade / DIV: DIV 03 Activity: Slab Rebar | Location: Tower A L05 Drawing Ref: S-105 Rev04 Spec Ref: 03 20 00-Rebar | WIR: WIR-RC-05-147 Test Ref: ITP (HP): ITP-RC-01 | Raised By: Consultant Responsible: RC Sub-01 Severity: Major | MS/ SD Ref: MS-RC-12 Target Date: 07/01/2026 Eng Disposition: Rectify | Verify Date: 07/01/2026 Evidence Ref: NCR-01-C1 Closure Date: 07/01/2026 | Payment Hold: None Notice Ref: Notice Date:
107-NCR-02 | 2026-01-04 | Open | Package: Structure Trade / DIV: DIV 03 Activity: Pour C30/37 | Location: Columns C2-C6 Drawing Ref: S-021 Spec Ref: 03 30 00 | WIR: WIR-CON-02-088 Test Ref: TR-026 ITP (HP): ITP-CON-02 | Raised By: Consultant Responsible: Contractor Severity: Critical | MS/ SD Ref: MS-CON-04 Target Date: 12/01/2026 Eng Disposition: Pending | Verify Date: Evidence Ref: Awaiting Closure Date: | Payment Hold: IPC-05 Notice Ref: Notice Date:
107-NCR-03 | 2026-01-05 | Under Review | Package: Waterproofing Trade / DIV: DIV 07 Activity: Roof Membrane | Location: Podium Zone R3 Drawing Ref: AR-11 Rev02 Spec Ref: 07 10 00 | WIR: WIR-WP-01-031 Test Ref: FT-003 ITP (HP):WP-01 HP-01 | Raised By: Contractor QA Responsible: WP Sub-02 Severity: Major | MS/ SD Ref: MS-WP-06 Target Date: 10/01/2026 Eng Disposition: Repair | Verify Date: 11/01/2026 Evidence Ref: FT-04+photo Closure Date: 11/01/2026 | Payment Hold: IPC-05 Notice Ref: Notice Date:
107-NCR-04 | 2026-01-06 | Action | Package: MEP Trade / DIV: DIV 22 Activity: Firestopping | Location: MEP riser Drawing Ref: MEP-FS-07 Spec Ref: 07 84 00 | WIR: WIR-FS-03-019 Test Ref: ITP (HP): FS-01 HP-02 | Raised By: Consultant Responsible: MEP Sub-03 Severity: Major | MS/ SD Ref: MS-FS-02 Target Date: 13/01/2026 Eng Disposition: Rectify | Verify Date: 14/01/2026 Evidence Ref: Photo 019-A Closure Date: | Payment Hold: IPC-06 Notice Ref: Notice Date:
107-NCR-05 | 2026-01-07 | Open | Package: Steel Trade / DIV: DIV 05 Activity: Beam welding | Location: L04 Grid D-2 Drawing Ref: S-204 Rev05 Spec Ref: 05 12 00 | WIR: WIR-STL-04-055 Test Ref: UT-017-Reject ITP (HP): STL-02 HP-04 | Raised By: Consultant Responsible: Steel Sub-01 Severity: Critical | MS/ SD Ref: MS-WELD-03 Target Date: 16/01/2026 Eng Disposition: Replace | Verify Date: Evidence Ref: Awaiting Closure Date: | Payment Hold: IPC-06 Notice Ref: NTC-002 Notice Date: 10/01/2026