## Planner
METHOD STATEMENT SUBMISSION TIMELINE PLANNER
| Project Name: |  | Project No: |  |  | Prepared By:
| Contractor: |  | Client: |  |  | Date: | 2026-05-20
| Contract Ref: |  | Site Location: |  |  | Revision:
| STATUS LEGEND: |  |  | ✔ Approved | ⚑ Pending | ✖ Overdue | ● In Review | ◌ Not Started
# | Method Statement / Activity | Activity Start Date | Review Period (days) | Resubmit Allowance (days) | Procurement Lead Time (days) | Permit Duration (days) | MS Submission Deadline | Review Completion | Submit Deadline | Procurement Start Date | Permit Expiry Date | Status
1 | Earthworks & Bulk Excavation | 2025-03-01 | 14 | 7 | 28 | 90 | — | — | — | — | 2025-05-30 | ◌ Not Started
2 | Piling Operations | 2025-03-15 | 14 | 7 | 28 | 90 | — | — | — | — | 2025-06-13 | ◌ Not Started
3 | Reinforced Concrete Works | 2025-03-08 | 14 | 7 | 28 | 90 | — | — | — | — | 2025-06-06 | ◌ Not Started
4 | Formwork & Falsework | 2025-03-22 | 14 | 7 | 28 | 90 | — | — | — | — | 2025-06-20 | ◌ Not Started
5 | Structural Steel Erection | 2025-03-15 | 14 | 7 | 28 | 90 | — | — | — | — | 2025-06-13 | ◌ Not Started
6 | Waterproofing & Tanking | 2025-03-29 | 14 | 7 | 28 | 90 | — | — | — | — | 2025-06-27 | ◌ Not Started
7 | Mechanical & Plumbing Installation | 2025-03-22 | 14 | 7 | 28 | 90 | — | — | — | — | 2025-06-20 | ◌ Not Started
8 | Electrical Installation & Cabling | 2025-04-05 | 14 | 7 | 28 | 90 | — | — | — | — | 2025-07-04 | ◌ Not Started
9 | HVAC System Installation | 2025-03-29 | 14 | 7 | 28 | 90 | — | — | — | — | 2025-06-27 | ◌ Not Started
12 | Roofing Works | 2025-04-19 | 14 | 7 | 28 | 90 | — | — | — | — | 2025-07-18 | ◌ Not Started
13 | Finishing Works – Internal | 2025-04-12 | 14 | 7 | 28 | 90 | — | — | — | — | 2025-07-11 | ◌ Not Started
14 | External Works & Landscaping | 2025-04-26 | 14 | 7 | 28 | 90 | — | — | — | — | 2025-07-25 | ◌ Not Started
15 | Commissioning & Testing | 2025-04-19 | 14 | 7 | 28 | 90 | — | — | — | — | 2025-07-18 | ◌ Not Started
SUMMARY
| Total Activities |  | Approved |  | Pending / In Review |  | Overdue |  | Not Started |  | Earliest Submission
| 13 |  | 0 |  | 0 |  | 0 |  | 13 |  | 00-Jan-1900
| generated by: | https://quollnet.com/methods/my
Formulas:
MS Submission Deadline = IFERROR(IF([Activity Start Date]="","",WORKDAY([Activity Start Date],-[Project No:]-[Resubmit Allowance (days)]-[Procurement Lead Time (days)],Holidays!$A2:A100)),"—")
Review Completion = IFERROR(IF([MS Submission Deadline]="","",WORKDAY([MS Submission Deadline],[Project No:],Holidays!$A2:A100)),"—")
Submit Deadline = IFERROR(IF([Review Completion]="","",WORKDAY([Review Completion],[Resubmit Allowance (days)],Holidays!$A2:A100)),"—")
Procurement Start Date = IFERROR(IF([Activity Start Date]="","",WORKDAY([Activity Start Date],-[Procurement Lead Time (days)],Holidays!$A2:A100)),"—")
Permit Expiry Date = IFERROR(IF([Activity Start Date]="","",[Activity Start Date]+[Prepared By:]),"—")

## Holidays
PUBLIC HOLIDAYS
Date | Description
2025-01-01 | New Year's Day
2025-04-18 | Good Friday
2025-04-21 | Easter Monday
2025-05-05 | Early May Bank Holiday
2025-05-26 | Spring Bank Holiday
2025-08-25 | Summer Bank Holiday
2025-12-25 | Christmas Day
2025-12-26 | Boxing Day
Add more holidays below ↓

## How To Use
HOW TO USE THIS PLANNER
INPUT FIELDS
| Activity Start Date (Col C) | Enter the planned date when site activity begins. All deadline calculations flow from this date.
| Review Period (Col D) | Number of working days your client/authority needs to review the method statement (typically 10–21 days).
| Resubmission Allowance (Col E) | Buffer working days allowed for preparing and resubmitting if comments are received (typically 5–10 days).
| Procurement Lead Time (Col F) | Working days required to procure materials/plant after approval. MS must be approved before procurement starts.
| Permit Duration (Col G) | Calendar days a permit/approval remains valid from the activity start date.
CALCULATED DATES
| MS Submission Deadline (Col H) | Activity Start - Review - Resubmission - Procurement (working days). Submit the MS by this date.
| Review Completion (Col I) | Submission Deadline + Review Period. Expected date of receiving client comments.
| Resubmission Deadline (Col J) | Review Completion + Resubmission Allowance. Latest date to re-submit with comments addressed.
| Procurement Start (Col K) | Activity Start - Procurement Lead Time. Earliest date procurement can begin (requires approval first).
| Permit Expiry (Col L) | Activity Start + Permit Duration. Date by which all permitted work must be complete.
TIPS
| Holidays | Add all public/bank holidays in the 'Holidays' sheet. WORKDAY() automatically skips these.
| Status | Use the dropdown in column M to update each activity's current status.
| Adding Rows | Copy a row in the data range (9–38) and paste it below to extend the tracker.
| Dates | Enter dates in DD-MMM-YYYY format or use Excel's date picker for accuracy.