## Deviation Request Form
[ Contractor Logo ] |  | METHOD STATEMENT DEVIATION / DEPARTURE REQUEST FORM | [5 empty] | [ Consultant / Client Logo ]
A — DOCUMENT CONTROL
Project Name |  |  |  | Contract No.
Employer / Client |  |  |  | Consultant / Engineer
Contractor |  |  |  | Subcontractor / Specialist (if applicable)
Form No. |  |  |  | Request No.
Revision |  |  |  | Date Submitted
Submitted By |  |  |  | Discipline
Location / Zone / Area |  |  |  | Related Activity
Related Method Statement Ref. |  |  |  | Method Statement Revision
Related ITP Ref. |  |  |  | Related Drawing Ref.
Related Spec. Section / Clause |  |  |  | Related Material Approval Ref.
Related RFI / SI / NCR Ref. (if any) |  |  |  | Related Permit / EHS Ref.
B — TYPE OF DEPARTURE REQUESTED (select all that apply)
☐ | Departure from approved method statement |  |  |  | ☐ | Departure from ITP / inspection requirement
☐ | Departure from specification |  |  |  | ☐ | Departure from testing requirement
☐ | Departure from drawing |  |  |  | ☐ | Departure from manufacturer recommendation
☐ | Departure from approved sequence |  |  |  | ☐ | Departure from temporary works arrangement
☐ | Departure from approved material |  |  |  | ☐ | Departure from permit / access condition
☐ | Departure from approved equipment |  |  |  | ☐ | Other (describe in Section D)
C — DESCRIPTION OF APPROVED REQUIREMENT
State the current approved or contractual requirement. Quote the relevant method statement section, specification clause, drawing note, ITP item, or approved document reference.
D — DESCRIPTION OF PROPOSED DEPARTURE
Describe exactly what the contractor proposes to change. Be specific about method, material, equipment, sequence, inspection, testing, safety, or environmental control.
E — REASON FOR DEPARTURE
Primary Reason |  |  |  | If 'Other', specify:
Detailed explanation of reason:
F — TECHNICAL JUSTIFICATION
Explain why the proposed departure is technically acceptable. Attach calculations, manufacturer recommendations, specialist statement, sketches, risk assessment, or supporting data where required.
G — IMPACT ASSESSMENT
Impact Area |  | Yes / No / N/A |  | Description / Remarks |  |  |  |  | Supporting Doc. Required?
Contract compliance
Quality / workmanship
Safety
Environment
Sustainability
Inspection and testing
ITP hold / witness points
Programme / schedule
Cost / variation
Procurement / lead time
Warranty / guarantee
Authority approval
Temporary works
Interface with other trades
Operation and maintenance
H — RISK REVIEW
Does this departure require risk assessment update?
Does this departure require HSE approval?
Does this departure require toolbox talk / briefing update?
Risk rating BEFORE controls: |  |  |  |  | Risk rating AFTER controls:
Key additional controls required:
I — QA/QC AND INSPECTION REVIEW
Does the ITP need revision?
Are additional inspections required?
Are additional tests required?
Is a hold point affected?
Is a witness point affected?
WIR requirements / remarks:
Acceptance criteria after departure:
J — COMMERCIAL / CONTRACT REVIEW
Does this departure affect cost?
Does this departure affect time?
Does this require a variation order?
Does this require a contractual notice?
Does this require a formal instruction?
Contract / commercial remarks:
K — ATTACHMENTS CHECKLIST
Attachment |  |  |  | Required? |  | Attached? |  | Attachment Ref. |  | Remarks
Revised method statement section
Marked-up drawings
Revised ITP
Revised risk assessment
Manufacturer recommendation letter
Specialist subcontractor proposal
Engineering calculations
Temporary works design / check certificate
Material data sheet (MDS)
Test certificate / results
Photographs / site condition evidence
RFI / clarification document
Programme impact assessment
Cost impact assessment
Other
L — CONTRACTOR INTERNAL REVIEW AND APPROVAL
Role |  |  | Signature |  | Date |  | Comments
Prepared by
Site Engineer
QA/QC Engineer
HSE Officer
Planning Engineer
Procurement Representative
Specialist Subcontractor
Construction Manager
Project Manager
Commercial Manager (if cost / time affected)
M — CONSULTANT / ENGINEER DECISION
DECISION:
Consultant / Engineer Comments:
Conditions of Acceptance:
Documents to be revised before implementation:
Required inspections / tests before work proceeds:
⚠ Does this acceptance constitute formal acceptance of a departure from the specification?
Confirmation on specification departure:
Reviewed by |  | Name |  |  | Signature |  |  | Date
Lead Engineer / Resident Engineer
Principal Engineer / Design Manager
Employer Representative (if required)
N — IMPLEMENTATION CONTROL
Approved departure may be implemented from date: | [7 empty] | Date to be confirmed upon approval
Area / scope where departure applies:
Is this one-time or permanent for the activity?
Required method statement revision reference:
Required ITP revision reference:
Required briefing date:
Responsible person for implementation:
Close-out evidence required:
Close-out date:
O — REVISION HISTORY
Rev | Date |  |  |  | Prepared by |  | Reviewed by |  | Status

## Guidance Notes
GUIDANCE NOTES — Method Statement Deviation / Departure Request Form
1. Purpose of this Form
This form is a controlled document used when a contractor wishes to depart from any approved method statement, specification, drawing, ITP, or other contractually approved requirement. It is NOT a routine method statement revision form. It captures the departure formally, records technical justification, assesses impacts, and obtains consultant / client approval before implementation.
2. When to Use This Form
• | The contractor wishes to change an approved method but the specification requirement remains unchanged.
• | A material or equipment substitution is proposed that differs from the approved or specified item.
• | A change in construction sequence, access, or temporary works arrangement is needed.
• | A manufacturer recommendation differs from the specified or approved method.
• | A site constraint, safety issue, or programme pressure requires a controlled deviation.
• | An ITP hold point, witness point, or test requirement may be missed, changed, or waived.
• | An environmental, permit, or HSE control condition requires modification.
3. When NOT to Use This Form
• | For routine method statement revisions that do not involve a departure from specification or approved drawings — use a normal method statement revision instead.
• | For requests for information or clarification — raise an RFI.
• | For claiming additional time or cost for a change directed by the employer — raise a variation notice.
• | For reporting non-conformances that have already occurred — raise a Non-Conformance Report (NCR).
4. Critical Distinction — Method Statement Approval vs Specification Compliance
Approval of a method statement — including a revised method statement — does NOT constitute automatic acceptance of a departure from the contract specification. The specification remains the binding contractual document unless a formal departure is accepted in writing. When submitting this form, always confirm with the consultant / engineer whether their approval constitutes a formal departure from the specification, or whether it is approval of the method only without relaxing the specification requirements.
5. Recommended Covering Wording
Include the following or similar wording in your transmittal or Section C when submitting:
"Please confirm whether approval of this Departure Request constitutes formal acceptance of a departure from Specification Clause [X], or whether acceptance is limited to the proposed method only, without altering the specification requirements."
6. When to Also Raise Other Documents
RFI: Where a specification, drawing, or scope is ambiguous or conflicting and clarification is needed before the departure request can be fully completed.
Site Instruction: Where the departure is being directed by the employer or consultant — the contractor should request a formal SI rather than submitting a departure request.
Variation Notice: Where the departure will result in additional cost or time, a formal variation notice or early warning must be issued in parallel with this form.
NCR: Where the departure has already been implemented without approval, an NCR must also be raised to record the non-conformance.
7. Implementation Rule
DO NOT implement the departure before written approval is received from the consultant / engineer. Any work carried out without approval will be treated as a non-conformance and may be subject to removal and replacement at the contractor's cost.
8. Document Control
• | Assign a unique Request No. for each departure request (e.g. DR-2024-001).
• | Revise the form using the Revision History table (Section O) — do not overwrite previous revisions.
• | Retain all attachments and supporting documents as part of the project quality record.
• | Update the method statement, ITP, and risk assessment after approval, and resubmit if required.
• | Record implementation close-out in Section N with evidence of briefing and updated documents.

## Dropdown Lists
Discipline | DepartureType | ReasonForDeparture | YesNo | YesNoNA | YesNoTBA | RiskRating | Decision | ReqAtt | AttYesNo | RevStatus | OneTimePerm | SpecDep
Civil | Departure from approved method statement | Site constraint | Yes | Yes | Yes | Low | Accepted | Required | Attached | Draft | One-time only | Yes – formal departure accepted
Structural | Departure from specification | Material availability | No | No | No | Medium | Accepted with comments | Not required | Not attached | Submitted | Permanent for this activity | No – acceptance limited to method only
Geotechnical | Departure from drawing | Specialist recommendation |  | N/A | To be assessed | High | Rejected | N/A | N/A | Reviewed | As described in scope below | Not applicable
Mechanical | Departure from approved sequence | Manufacturer recommendation |  |  |  | Critical | Revise and resubmit |  |  | Approved |  | To be clarified
Electrical | Departure from approved material | Safety improvement |  |  |  |  | For information only |  |  | Superseded
Instrumentation | Departure from approved equipment | Quality improvement |  |  |  |  | Requires formal instruction / variation
Piping | Departure from ITP / inspection requirement | Temporary works constraint |  |  |  |  | Requires further clarification
HVAC | Departure from testing requirement | Access / logistics issue
Architectural | Departure from manufacturer recommendation | Programme constraint
Fit-out | Departure from temporary works arrangement | Value engineering
Temporary Works | Departure from permit / access condition | Conflict between documents
Environmental | Other | Authority requirement
Health & Safety |  | Other
Other