## ITP - Concrete Works
| Quollnet.com |  | Project: |  | Contractor: |  |  |  |  | I.T.P
|  |  | XXX XXXX XXXXX - XXXX |  |  | ACME LLC
| contact@quollnet.com |  |  |  |  | contact@acme.com |  |  |  | Inspection test plan
Dates: |  |  | Contract Numnber / Trade: |  | Parties: |  |  |  | ITP Number . Revision
| Date Issued: |  | Civil/Strcture/Concrete Works |  | Prepared By: |  |  |  | 701-ITP-03-31 - Rev 2
| Date Approved: |  | Contract 701-25 |  | On Behalf of:
Legend: H = Hold (stop until release) · W = Witness (notify) · S = Surveillance/Review · C = Contractor · S/C = Subcontractor · E = Engineer/Client Rep · TPI = Third-Party Inspector.
Seq | Activity/Step | Inspectionn Test | References | Acceptance Criteria | Method Procedure | Frequency Sampling | Records | Resp | Pt | DM (min) | Remarks
1 | Mix Design Approval | Review & Approval | Project Specs; Mix Design; Codes | Approved mix design for element & exposure class | Document review | Per mix design / element | Approval stamp | C/E | H | 72h | Submit prior to any delivery
2 | Cement/Aggregates/Admixtures Certificates | Document Review | Mill/Test Certificates | Valid certificates & compliance to spec | Document review | Each supplier & lot | Certificates file | C | S | - | Retain in QA file
3 | Formwork/Erection & Cleanliness | Visual Inspection | Specs; Method Statement; Drawings | Correct dimensions; tight joints; clean; release agent applied | Checklist + visual | Each pour | Formwork checklist | C/E | W | 24h | Verify camber/lines, access & safety
4 | Reinforcement (Grade/Size/Spacing/Cover) | Visual & Measure | Rebar schedule; Specs; Codes | Correct grade/size; spacing; laps; cover blocks in place | Checklist + measurements | Each pour area | Rebar ITR | C/E | H | 24h | No pour without signed ITR
5 | Embedded Items/Anchors/Sleeves | Visual Check & Survey | Shop drawings; Specs | Location/tolerance within drawing; secured against movement | Survey/visual | Each pour area | Pre-pour checklist | C/E | W | 24h | Include conduits, waterstops, starters
6 | Pre-pour Coordination/Method Statement | Review & Briefing | Approved Method Statement | Team briefed; equipment ready; contingency measures in place | Toolbox talk | Each pour | TBT record; MS | C | S | - | Pump paths, vibrator count, backup power
7 | Batch Ticket Verification | Document & Visual | Spec; Mix Design | Batch time, mix code, water added recorded; within limits | Ticket review | Every truck | Batch ticket copies | C | S | - | Reject if out-of-time or wrong mix
8 | Concrete Temperature (Fresh) | Measurement | ASTM C1064 / EN 12350-7 | Within spec [e.g., 5–32°C or per spec] | Thermometer | Every truck | Test log | C | S | - | Hot/cold weather measures if out of range
9 | Slump/Workability | Field Test | ASTM C143 / EN 12350-2 | Within target [e.g., 75 ± 25 mm] unless otherwise specified | Slump cone | Every truck | Slump record | C | W | - | Record admixture/water additions
10 | Air Content (if specified) | Field Test | ASTM C231 / EN 12350-7 | Within specified range [e.g., 4–6%] | Pressure meter | Per spec frequency | Air content record | C | S | -
11 | Density/Unit Weight (if required) | Field Test | ASTM C138 / EN 12350-6 | Within expected density range | Field balance/measure | Per spec frequency | Density record | C | S | -
12 | Making Test Specimens | Sampling & Molding | ASTM C31 / EN 12390-2 | Specimens properly made, labeled, cured | Mold & initial cure | Per spec (e.g., 1 set/50 m³) | Cylinder / cube log | C/TPI | W | - | Secure curing boxes & transport
13 | Initial Placement Time | Observation | Spec; Mix Design | Within allowable time from batching | Check timestamps | Each pour | Pour log | C | S | -
14 | Placement Method & Drop Height | Observation | Spec; Method Statement | Drop height ≤ 1.5 m (or per spec); uniform placement | Visual | Continuous | Site diary | C/E | S | - | Use tremie/chutes if >1.5 m
15 | Vibration/Compaction | Observation | Spec; Method Statement | Complete consolidation; no segregation; working vibrators available | Visual; checklist | Continuous | Compaction record | C | S | - | Backup vibrators on site
16 | Construction/Pour Joints | Inspection | Joint details; Specs | Joint location & prep per detail; bonding agent where required | Visual; checklist | Each joint | Joint record | C/E | W | 24h
17 | Surface Finishing | Inspection | Spec; Finish class | Finish class as specified (float/trowel/broom) | Visual | Each area | Finish record | C | S | -
18 | Curing (Method & Duration) | Inspection | Spec; ACI/EN guidance | Method per spec (membrane/wet/blankets); duration ≥ specified | Visual; log | Each area | Curing log | C/E | S | - | Hot/windy: evaporation control
19 | Formwork Stripping | Inspection | Spec; Method Statement | Only after achieving required strength & time | Check test results | Each element | Stripping permit | C/E | W | 24h
20 | Surface Defects/Honeycombing | Inspection | Spec; Repair procedure | Acceptable per tolerance; repair method approved | Visual; hammer tap | Each element | Defect/NCR (if any) | C/E | S | -
21 | Compressive Strength Testing | Lab Test | ASTM C39 / EN 12390-3 | f'c ≥ [___] MPa at 28d (per spec & acceptance rules) | Lab testing | Per sampling plan | Lab reports | TPI/C | S | - | Include 7d (optional), 28d (mandatory)
22 | As-Built & Records Handover | Review | Spec; ISO 9001 | Complete and traceable records submitted | Document review | Per pour / milestone | ITP pack | C/E | S | - | Retain per contract retention period
Submitted By: |  |  | Reviewed by: |  | Approved by: |  |  |  | Comments:
date: |  |  | date: |  | date: |  |  |  | date: