## cashflow
Construction Tower
B + G + 28 + R Mixed Use (Residential and Commercial Tower with shops on the ground floor)
| Contract Value | 85000000 |  |  | Defect Liability Period | 12 |  |  | Release Retention @ End | 0.5
| Interest Rate | 1% |  |  | Advance Payment | 10% |  |  | Time for Payment | 4
| Project Duration | 24 |  |  | Retention | 10%
No. | Activity | Duration | Start | Cost | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41
1 | Site Mobilization | 6 | 0+0 | 5000000 | Retention 1: 833333.3333; 10% 2: 833333.3333; 10% 3: 833333.3333; 10% 4: 833333.3333; 10% 5: 833333.3333; 10% 6: 833333.3333
[5 empty] | 666666.6667 | 416666.6667 | 1016666.6667 | 783333.3333 | 750000 | 750000 | 333333.3333 | 158333.3333 | 0 | 0 | 0 | 0 | 125000
2 | Shoring | 2 | 1+0 | 6000000 | Retention 1: 0; 10% 2: 1694670.6609; 10% 3: 4305329.3391
[5 empty] | 0 | 709467.0661 | 430532.9339 | 3888000 | 702000 | 0 | 0 | 0 | 0 | 270000
3 | Excavation | 3 | 2+0 | 1000000 | Retention 1: 0; 10% 2: 0; 10% 3: 155646.6211; 10% 4: 688706.7578; 10% 5: 155646.6211
[5 empty] | 0 | 0 | 0 | 0 | 759918.041 | 140081.959 | 50000 | 0 | 50000
4 | Piling | 4 | 3+0 | 7000000 | Retention 1: 0; 10% 2: 0; 10% 3: 0; 10% 4: 215395.6809; 10% 5: 1761720.0901; 10% 6: 3877805.1894; 10% 7: 1145079.0396
[5 empty] | 0 | 0 | 0 | 651539.5681 | 176172.009 | 1668951.5386 | 2769678.0022 | 1021213.1913 | 397445.6908 | 0 | 0 | 0 | 0 | 315000
5 | Concrete Works | 12 | 4+0 | 20000000 | Retention 1: 0; 10% 2: 0; 10% 3: 0; 10% 4: 0; 10% 5: 116749.1995; 10% 6: 266681.2225; 10% 7: 577569.6023; 10% 8: 1191975.2953; 10% 9: 2234418.1435; 10% 10: 3493221.0373; 10% 11: 4143116.9205; 10% 12: 3561448.4648; 10% 13: 2309388.9817; 10% 14: 1238567.3687; 10% 15: 597214.1668; 10% 16: 269649.597
[5 empty] | 0 | 0 | 0 | 0 | 1058374.5998 | 133340.6113 | 426819.7531 | 819249.9214 | 1569422.9622 | 2598680.0621 | 3418494.7594 | 3411975.1653 | 2602540.615 | 1593121.6563 | 836866.8954 | 399364.5933 | 120962.4216 | 510785.9839 | 0 | 0 | 0 | 0 | 500000
6 | Masonry | 10 | 8+0 | 1000000 | Retention 1: 0; 10% 2: 0; 10% 3: 0; 10% 4: 0; 10% 5: 0; 10% 6: 0; 10% 7: 0; 10% 8: 0; 10% 9: 11668.1587; 10% 10: 30456.9766; 10% 11: 73276.2475; 10% 12: 151558.9548; 10% 13: 233039.6625; 10% 14: 233039.6625; 10% 15: 151558.9548; 10% 16: 73276.2475; 10% 17: 30456.9766; 10% 18: 11668.1587
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73500.4476 | 9137.093 | 40854.9348 | 83013.4604 | 146017.2502 | 191288.2705 | 175969.8974 | 115981.7282 | 58939.4548 | 25352.1128 | 8638.5165 | 36306.8338 | 0 | 0 | 0 | 0 | 35000
7 | MEP | 12 | 8+0 | 22000000 | Retention 1: 0; 10% 2: 0; 10% 3: 0; 10% 4: 0; 10% 5: 0; 10% 6: 0; 10% 7: 0; 10% 8: 0; 10% 9: 428439.0376; 10% 10: 930107.2588; 10% 11: 1854397.4779; 10% 12: 3205018.5353; 10% 13: 4379118.2772; 10% 14: 4387579.8732; 10% 15: 3224695.5679; 10% 16: 1877566.4887; 10% 17: 954912.1291; 10% 18: 456060.7036; 10% 19: 210967.1016; 10% 20: 91137.5489
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2111421.9519 | 46505.3629 | 92719.8739 | 160250.9268 | 218955.9139 | 3633734.9424 | 3954221.1085 | 3426509.7842 | 2763651.8597 | 1756898.9967 | 946646.7672 | 464901.1372 | 216216.3385 | 96585.6752 | 1065779.3611 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1045000
8 | FInishing | 10 | 12+0 | 12000000 | Retention 1: 0; 10% 2: 0; 10% 3: 0; 10% 4: 0; 10% 5: 0; 10% 6: 0; 10% 7: 0; 10% 8: 0; 10% 9: 0; 10% 10: 0; 10% 11: 0; 10% 12: 0; 10% 13: 307217.8321; 10% 14: 762551.4682; 10% 15: 1636928.3538; 10% 16: 2678583.1451; 10% 17: 2897261.27; 10% 18: 2017105.9673; 10% 19: 1019778.9147; 10% 20: 438100.5941; 10% 21: 176450.1347; 10% 22: 66022.3201
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 932165.3496 | 228765.4405 | 850520.991 | 1593211.1937 | 2135854.269 | 2178614.2014 | 1632667.8039 | 925907.6302 | 428567.3169 | 177228.4744 | 61708.3297 | 434788.9997 | 0 | 0 | 0 | 0 | 420000
9 | Facacde | 10 | 12+0 | 6000000 | Retention 1: 0; 10% 2: 0; 10% 3: 0; 10% 4: 0; 10% 5: 0; 10% 6: 0; 10% 7: 0; 10% 8: 0; 10% 9: 0; 10% 10: 0; 10% 11: 0; 10% 12: 0; 10% 13: 183564.4296; 10% 14: 447589.8013; 10% 15: 923745.5936; 10% 16: 1409796.1168; 10% 17: 1398077.9673; 10% 18: 905555.4977; 10% 19: 440262.2034; 10% 20: 187224.6921; 10% 21: 75884.2275; 10% 22: 28299.4708
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 558356.443 | 44758.9801 | 92374.5594 | 140979.6117 | 139807.7967 | 90555.5498 | 2242864.2703 | 1417481.6043 | 425080.5607 | 192287.8278 | 78686.1841 | 30653.9264 | 276112.6857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 270000
10 | Wood Works | 10 | 12+0 | 1000000 | Retention 1: 0; 10% 2: 0; 10% 3: 0; 10% 4: 0; 10% 5: 0; 10% 6: 0; 10% 7: 0; 10% 8: 0; 10% 9: 0; 10% 10: 0; 10% 11: 0; 10% 12: 0; 10% 13: 45405.5375; 10% 14: 105048.71; 10% 15: 194249.8247; 10% 16: 248803.8243; 10% 17: 203576.7745; 10% 18: 114786.4424; 10% 19: 52607.9976; 10% 20: 22500.384; 10% 21: 9498.2337; 10% 22: 3522.2713
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 184540.5537 | 10504.871 | 19424.9825 | 24880.3824 | 20357.6774 | 262560.3156 | 292500.2005 | 54979.287 | 24608.9636 | 10431.7917 | 4101.4591 | 46109.5154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000
11 | Handing Over | 3 | 21+0 | 800000 | Retention 1: 0; 10% 2: 0; 10% 3: 0; 10% 4: 0; 10% 5: 0; 10% 6: 0; 10% 7: 0; 10% 8: 0; 10% 9: 0; 10% 10: 0; 10% 11: 0; 10% 12: 0; 10% 13: 0; 10% 14: 0; 10% 15: 0; 10% 16: 0; 10% 17: 0; 10% 18: 0; 10% 19: 0; 10% 20: 0; 10% 21: 0; 10% 22: 266666.6667; 10% 23: 266666.6667; 10% 24: 266666.6667
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 173333.3333 | 133333.3333 | 325333.3333 | 117333.3333 | 30666.6667 | 0 | 0 | 0 | 0 | 20000
| Total Work |  |  | 85000000 | Retention 1: 865933.1703; 10% 2: 2626899.016; 10% 3: 5501421.6376; 10% 4: 1805403.9196; 10% 5: 2979623.2976; 10% 6: 5172551.08; 10% 7: 1790038.3198; 10% 8: 1238605.1357; 10% 9: 2779152.248; 10% 10: 4628016.4814; 10% 11: 6308278.7885; 10% 12: 7188657.777; 10% 13: 7749479.8442; 10% 14: 7455037.1042; 10% 15: 6991605.8587; 10% 16: 6814210.3991; 10% 17: 5698829.2786; 10% 18: 3642298.5992; 10% 19: 1791043.7466; 10% 20: 767871.3157; 10% 21: 272075.4358; 10% 22: 378770.3172; 10% 23: 277098.6145; 10% 24: 277098.6145
| Total Inflow |  |  | 85000000 | 8500000 | 0 | 0 | 0 | 692746.5363 | 1891367.2915 | 4171175.5003 | 1740004.5531 | 2289761.0879 | 3962606.6414 | 1702631.6767 | 1034998.7633 | 2100078.0294 | 3554504.0465 | 4912202.0463 | 5680495.9025 | 6154718.11 | 5987585.1026 | 5630359.1866 | 5465559.956 | 4648293.9125 | 3078361.3337 | 1580935.3855 | 696150.847 | 257324.0191 | 294480.6632 | 229812.6278 | 221678.8916 | 4272167.8892 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4250000
| Total Outflow |  |  | 81800000 | 666666.6667 | 1126133.7328 | 1447199.6006 | 5322872.9014 | 3446464.6498 | 2692374.1088 | 3579831.0886 | 1998796.446 | 4201791.0525 | 2924322.518 | 3552069.5681 | 3655239.5525 | 4767576.1254 | 6017174.1608 | 5929378.4342 | 5700927.2934 | 5239573.4792 | 4824767.1602 | 5123317.5583 | 2899576.4925 | 1094473.1797 | 649867.1024 | 1843608.6674 | 836885.7749 | 428446.019 | 30666.6667 | 0 | 0 | 420000 | 0 | 20000 | 0 | 0 | 1045000 | 45000 | 270000
| Netflow |  |  | 3200000 | 7833333.3333 | -1126133.7328 | -1447199.6006 | -5322872.9014 | -2753718.1135 | -801006.8173 | 591344.4117 | -258791.8929 | -1912029.9647 | 1038284.1234 | -1849437.8915 | -2620240.7892 | -2667498.096 | -2462670.1144 | -1017176.3879 | -20431.3909 | 915144.6307 | 1162817.9424 | 507041.6282 | 2565983.4636 | 3553820.7328 | 2428494.2313 | -262673.2819 | -140734.9278 | -171122 | 263813.9966 | 229812.6278 | 221678.8916 | 3852167.8892 | 0 | -20000 | 0 | 0 | -1045000 | -45000 | -270000 | 0 | 0 | 0 | 0 | 4250000
| Cash with Interest |  |  | 955025.1966 | 7833333.3333 | 6707199.6006 | 5260000 | -63501.6304 | -2845391.9414 | -3682862.7463 | -3122433.5179 | -3415037.6649 | -5380338.3059 | -4385474.7243 | -6297261.742 | -9006677.5564 | -11790917.4089 | -14396123.3985 | -15567432.7843 | -15743742.8169 | -14976884.168 | -13952206.8879 | -13579616.9123 | -11123769.7832 | -7645648.5409 | -5269325.8527 | -5587319.126 | -5785334.5943 | -6016021.1602 | -5809729.2353 | -5635715.7736 | -5468177.2508 | -1632169.4552 | -1648491.1498 | -1685176.0613 | -1702027.8219 | -1719048.1001 | -2791688.5811 | -2865055.4669 | -3166406.0216 | -3198070.0818 | -3230050.7826 | -3262351.2905 | -3294974.8034 | 955025.1966