## Sheet1
|  | Company Name |  | Site Clarification | [5 empty] | Form
|  | Address | [7 empty] | ID
|  | email, phone | [7 empty] | Revision
PROJECT NAME
Project address, street, city, country, project number, project reference
Employer: | Emp Developers |  |  |  | Consultant: | LTD Engineers
(reviewer)
Main Contractor: |  | Main Contractor LTD |  |  | Sub Contractor: | Sub Contractor LTD
(originator) |  |  |  |  | (optional)
SC ID: |  |  | Revision: |  |  | Date: |  |  | DIV:
Disipline: |  |  | Package: |  |  | Needed by: |  |  | Priority:
References: (Drawing refs, Spec ref)
Question:
Proposed options / solution:
Proposed options are provided for consideration only and do not constitute an instruction. If a change to method/spec/quantity/sequence is required, please issue a formal Site Instruction and, if time/cost is affected, a Variation/Change Order.
Contractor Representative: |  |  |  |  | Contractor Signature
X
Consultant Review |  |  | Date Reviewed: |  |  |  | Approval Status Code
[7 empty] | A | Clarification - No Change
[7 empty] | B | Instruction to follow
[7 empty] | C | VO to follow
[7 empty] | D | Further Info Required
[7 empty] | E | Not Agreed / Rejected
Consultant Representative: |  |  |  |  | Consultant Signature
X
Attachments:
How to fill the Site Clarification (RFI/TQ) form
A) Header & project block
1. Company header
Your company name, address, email, phone (usually auto-filled).
2. Form ID / Revision
Form ID: your internal template ID (e.g., QNL-SC-01).
Revision: template revision (e.g., Rev 1.2). Not the SC revision.
3. Project name & details
Project name, full address, project number/reference.
4. Parties
Employer: Client/Owner company name.
Consultant (reviewer): Engineer/Consultant firm.
Main Contractor (originator): Your company.
Subcontractor (optional): If they drafted the query.
B) Clarification metadata (top grid)
5. SC ID
Unique number matching your log (e.g., SC-2025-QNL-042).
6. Revision (of this SC)
Start at 0 (or A). Increment if you resubmit with changes.
7. Date
Date of submission.
8. DIV (optional/house field)
Use for your internal code (e.g., distribution index, doc version). If not used, leave blank.
9. Discipline
Architectural / Structural / MEP / Civil / Interiors / Facade / Other.
10. Package
Work package (e.g., Concrete Frame, MEP 2nd Fix).
11. Needed by
The decision date aligned to your look-ahead (e.g., +5 working days). This drives your SLA and chasing.
12. Priority
Low / Medium / High / Critical (if it threatens the critical path).
C) References
13. References (Drawing refs, Spec ref)
Drawings: sheet + revision (e.g., S-202 Rev B).
Specs: section codes (e.g., 03 30 00 Concrete).
BoQ/Detail numbers if relevant. Keep it tight and exact.
D) The question (the core of the form)
14. Question
One clear question, 1–3 sentences, single topic.
State context briefly, then the precise ask.
Example: “Please confirm slab edge depth and starter bar spacing at Grid B5 to coordinate façade anchors per S-202 Rev B and Spec 03 30 00.”
E) Proposed options / solution (optional but recommended)
15. Proposed options / solution
Provide Option A/B with short notes (time/cost/risks).
Example: Option A: Edge 250 mm with 12@150 (no anchor clash; +1 day formwork). Option B: Edge 225 mm with 12@125 (risk at anchors; no extra time).
Keep the included disclaimer: “For consideration only; not an instruction. If change required, issue SI/VO.”
F) Contractor sign-off
16. Contractor Representative & Signature
Name, role, signature/date (digital is fine). This confirms the query is complete and ready for review.
G) Consultant review & decision
17. Date Reviewed
The consultant’s review date (filled by reviewer).
18. Approval Status Code (tick one)
A – Clarification – No Change: Interpretation only; proceed per reply; update docs if needed.
B – Instruction to follow: A Site Instruction (SI) will be issued; do not proceed on change until SI arrives.
C – VO to follow: A Variation/Change Order will be processed (time/cost).
D – Further Info Required: Provide the requested info; resubmit as next SC revision.
E – Not Agreed / Rejected: No approval; see notes.
19. Consultant Representative & Signature
Name/role + signature. If B/C is ticked, they should reference the forthcoming SI/VO number when available.
H) Attachments
20. Attachments
List filenames (e.g., Ma_S-202-B5.png; Photo_B5.jpg; Sketch_01.pdf). Use cropped, annotated views (avoid whole sheets).