## Checklist
3D Concrete Printing During-Print Quality Inspection Checklist
Completed by: |  |  | Date:
See Instructions for guidance. Record results and notes in the shaded cells.
No. | Section | Check / Requirement | Result | Notes / Evidence
1 | Process identity | Wall/segment and current approved print-file revision match the active production run.
2 | Process identity | Material batch and required printer/process monitoring records are traceable to this visit.
3 | Extrusion and geometry | Extrusion is continuous without unacceptable gaps, under-extrusion or over-extrusion.
4 | Extrusion and geometry | Measured bead width and layer height meet approved tolerances at required sampling locations.
5 | Extrusion and geometry | Layer alignment and contact are within the approved geometry requirements.
6 | Extrusion and geometry | Wall position and developing geometry remain within approved setting-out tolerances.
7 | Buildability and system control | No progressive slumping, bulging, leaning or loss of stability is observed.
8 | Buildability and system control | Nozzle clearance is appropriate; no unacceptable drag, collision or deposited-layer disturbance is observed.
9 | Buildability and system control | Layer intervals and material age remain within the qualified process window.
10 | Buildability and system control | Process/environmental parameters remain within the approved operating range.
11 | Interfaces and defects | Required reinforcement/embedded items installed during this visit are checked before concealment under the applicable ITP.
12 | Interfaces and defects | Visible defects or deviations are identified, located, recorded and escalated under the project procedure.
13 | Visit disposition | Any failed critical condition has led to the required hold, notification or engineering disposition before proceeding.

## Instructions
3D Concrete Printing During-Print Quality Inspection Checklist
Complete this checklist for one defined observation visit during active printing of a wall or segment. Repeat the checklist for later visits. Record location/layer, measurements and process context in the inspection record; compare with the approved model, qualified printing parameters and project ITP. Stop or escalate when continued printing could conceal a critical defect or create instability.
Record Done, Not done or N/A. Use Notes / Evidence for observations and follow-up.
Project / Location: ____________________