## Checklist
3D Printed Concrete Reinforcement and Embedded Services Inspection Checklist
Completed by: |  |  | Date:
See Instructions for guidance. Record results and notes in the shaded cells.
No. | Section | Check / Requirement | Result | Notes / Evidence
1 | Design and coordination | Current approved reinforcement/MEP coordination drawings identify the elements to be inspected.
2 | Design and coordination | The print file and intended layer/cavity arrangement accommodate the approved reinforcement and embeds.
3 | Reinforcement and anchors | Required reinforcing bars, anchors or connectors have the approved type, size and grade.
4 | Reinforcement and anchors | Reinforcement positions, spacing, laps and cover/clearances satisfy the approved structural details.
5 | Reinforcement and anchors | Starter bars, connection hardware and required supports are correctly located and secured.
6 | Cavities and grout interfaces | Required ducts and grout cavities remain accessible, unobstructed and dimensionally suitable.
7 | Cavities and grout interfaces | Any prescribed grout preparation/placement stage and inspection prerequisites are satisfied before covering.
8 | MEP and openings | Conduits, boxes, sleeves and penetrations are in the approved locations.
9 | MEP and openings | Embedded services and supports do not conflict with reinforcement, structural connections or the print path.
10 | MEP and openings | Required fire/water/air sealing and movement details are provided or identified for the correct follow-on stage.
11 | Evidence and release | Photos/measurements identify the wall, elevation or layer before the work is concealed.
12 | Evidence and release | Critical deviations have been referred for designer/engineer disposition rather than field modification.
13 | Evidence and release | Required pre-concealment hold/witness inspections and release authorization have been recorded.

## Instructions
3D Printed Concrete Reinforcement and Embedded Services Inspection Checklist
Complete at a defined hold or witness visit before specified reinforcement, anchors, sleeves, boxes or other critical embedded items become concealed by printing, grouting or closing the wall. Inspect only the elements relevant to this visit and mark genuinely inapplicable checks N/A. Do not allow concealment where required engineering inspection or release is outstanding.
Record Done, Not done or N/A. Use Notes / Evidence for observations and follow-up.
Project / Location: ____________________