## Sheet1
Generated file by QChecklists
https://quollnet.com/checklist
Drill bored piles > 600 mm inspection checklist – drilling
Drill bored piles > 600 mm interactive checklist for drilling inspection; commentable records with verticality and base sediment logs, plus export as PDF/Excel for approvals.
Project:
| Filled by: |  | Date:
Pre-Drill Planning and Setup
1 | Confirm latest IFC drawings and pile schedule; verify pile diameter ≥ 600 mm and design toe level.
2 | Set out pile center using total station; tolerance ≤ 10 mm or per specs; capture as-built coordinates and stake photo.
3 | Verify platform level (±20 mm) and bearing per geotechnical signoff; record plate-load or engineer approval with photos.
4 | Conduct drilling briefing covering strata, slurry/dry method, verticality tolerance, and hold points; file signed toolbox talk.
Rig and Tooling Verification
5 | Confirm rig torque, crowd, and stroke meet design depth/diameter; attach rig data sheet and serial number photo.
6 | Calibrate depth counter and dual-axis inclinometer; keep certificates ≤ 6 months; record zero checks with photos.
7 | Inspect buckets/augers/core barrels; measure effective diameter not less than design; photo with tape and tooling ID.
8 | Check temporary casing straightness and joints; trial assemble; document roll test and diameter gauge readings.
Drilling Operations Control
9 | Confirm drilling method (dry, bentonite, or polymer) per approved method statement; upload approval reference.
10 | Record start time, weather, groundwater level, and initial strata; attach site log with readings and photos.
11 | Control rotation and crowd to prevent overbreak/necking; log RPM, crowd pressure, and penetration rates by depth.
12 | If slurry used, test density (1.05–1.15 g/cm³), viscosity (32–50 s), sand content per supplier/specs; log every 2 h with kit photos.
13 | Measure actual diameter at casing top and first 3 m using calipers/tape; not less than design; record readings and photos.
14 | Track depth with weighted tape or electronic sensor; confirm ≥ design toe; timestamped depth log signed by driller.
Verticality and Geometry Documentation
15 | Check verticality at casing with spirit level and dual-axis inclinometer; deviation ≤ 1% or per specs; capture readings/photos.
16 | Perform downhole verticality survey at final depth (inclinometer/televiewer); upload profile report and instrument serial.
17 | Verify pile center vs survey control after drilling; tolerance ≤ 25 mm or per specs; attach as-built survey.
18 | Record zones of overbreak or constriction; measure diameters by depth interval; add annotated photos with scales.
Base Clean-Out and Sediment Assessment
19 | Clean base with clean-out bucket/airlift until returns run clear; photograph last two loads and logging notes.
20 | Measure base sediment at center and four quadrants using weighted spoon or sampler; ≤ 50 mm or per specs; log values/photos.
21 | Confirm base level and formation description (soil/rock); obtain geotechnical verification; attach signed inspection sheet.
QA Records and Handover (Non-Concreting)
22 | Compile drilling log: depth, strata, tool changes, slurry tests, delays; driller and supervisor signatures required.
23 | Attach verticality reports, diameter checks, sediment measurements, and calibration certificates; upload to lot file with QR link.
24 | Issue ITP hold-point release for concreting; confirm scope excludes concreting activities; obtain approvals and distribute.
Comments
Filled by:
Signature:
Introduction |  |  | How to use this checklist
Drill bored piles > 600 mm require the same controls scaled to a larger diameter, with rigorous documentation of verticality and base sediment, and this checklist focuses strictly on drilling. It supports large-diameter bored piles and bored pile drilling activities, providing practical drilling inspection steps that prevent misalignment, necking, excessive overbreak, and contaminated bases. By standardizing pre-drill planning, rig/tooling verification, drilling operations, verticality checks, and base clean-out assessment, teams reduce rework, protect geotechnical capacity, and hand over a clean, compliant hole for subsequent concreting. The scope excludes concreting operations entirely; acceptance cues reference the approved project specifications and authority requirements. Use this interactive checklist to tick items, add time-stamped comments, attach readings and photos, and export PDF/Excel; a QR code secures the record for field verification. |  |  | 1. Preparation: Gather calibrated inclinometer, depth counter, survey equipment, mud balance/Marsh funnel (if slurry), clean-out tools, camera, and PPE. Review approved method statement and project specifications. Confirm platform readiness and permissions before starting drilling activities. 2. Using the Interactive Checklist: Start interactive mode, tick items as completed, and add time-stamped comments with photos, readings, and serial numbers. Tag stakeholders where action is needed. Export the evolving record to PDF/Excel at milestones for review. 3. Sign-Off: After completing drilling, verticality, and base sediment checks, obtain digital signatures from driller, supervisor, and geotechnical representative. Distribute the export and archive it with a QR-authenticated link for future verification.