## Sheet1
Generated file by QChecklists
https://quollnet.com/checklist
Apply vertical spray-applied membranes: QA and adhesion
Apply vertical spray-applied membranes with an interactive checklist for coverage, rebound, adhesion, and protection; commentable and export as PDF/Excel.
Project:
| Filled by: |  | Date:
Pre-Application Verification
1 | Confirm the system is spray-applied (not brush/roller liquid-applied); record product name, data sheet, and approvals; obtain supervisor sign-off.
2 | Inspect vertical substrate soundness; remove laitance and weak material; verify clean, dry, dust-free surface; photo evidence with scale and date.
3 | Measure substrate moisture with a calibrated meter; acceptance: ≤5% w/w or per approved project specifications; log readings and device serial number.
4 | Record environmental conditions: 5–35 °C, RH ≤85%, substrate ≥3 °C above dew point; use calibrated psychrometer; attach screen/photo evidence.
5 | Mask adjacent finishes and install ground-level catch boards/tarps within 0.5 m of wall; photo coverage before spraying.
Equipment and Spray Setup
6 | Verify spray equipment calibration per manufacturer: ratio within ±2% of target; record pressures/temperatures; capture system printout or dashboard photo.
7 | Prepare materials per data sheet; record batch/lot numbers and expiry; retain labels and delivery dockets as evidence.
8 | Create a 0.5 m² vertical mock-up; confirm finish, coverage, and rebound management; obtain client/consultant approval signature and photos.
9 | Set spray fan, tip, and standoff distance (300–450 mm or per manufacturer); verify uniform pattern on test card; photo pattern.
Coverage and Rebound Control
10 | Apply in multiple light passes with 50% overlap to avoid sagging; no visible runs; supervisor visual check recorded with photos.
11 | Measure wet film thickness (WFT) using a comb gauge: ≥5 locations per 10 m²; acceptance: average at target, none below minimum.
12 | After cure, measure dry film thickness (DFT) by ultrasonic gauge on a 1 m grid; acceptance: ≥95% area within −10%/+15% of target; no point below minimum.
13 | Collect rebound after each lift; weigh and log mass; acceptance: ≤10% by mass relative to sprayed output; photo bagged waste.
14 | Prohibit reuse of rebound; dispose per site environmental plan; attach disposal ticket and supervisor confirmation.
15 | Detail corners and penetrations with fillets or sealant per system; minimum 10 mm radius; photo continuous coverage without pinholes.
Adhesion and Curing Verification
16 | Conduct pull-off adhesion tests with 50 mm dollies: min 5 per 100 m²; acceptance: ≥1.0 MPa or per approved project specifications and authority requirements; record values and failure modes.
17 | Confirm cure readiness: tack-free check and hardness per data sheet; record time-since-application and measured hardness values.
18 | Perform holiday detection on cured membrane where applicable using high-voltage spark testing; acceptance: zero holidays; mark, repair, and retest; photo evidence.
Protection and Detailing
19 | Install mechanical protection (e.g., 3–6 mm boards or 300 g/m² geotextile) before backfilling or adjacent works; photo full-height coverage.
20 | Verify UV stability; if non-UV-stable, overcoat or conceal within manufacturer’s stated window; record dates/times and photos.
21 | Coordinate terminations with termination bars, sealant, or flashings; continuous bead and fixings at specified centres; photo close-ups.
Documentation and Handover
22 | Confirm exclusion of brush/roller liquid-applied systems in this work package; upload supervisor statement and product installation evidence.
23 | Final inspection on 1 m grid: recheck DFT at random points, verify repairs closed; attach as-built photos with measuring scale.
24 | Compile dossier: data sheets, lot numbers, calibration records, WFT/DFT logs, adhesion results, repairs; obtain stakeholder sign-offs.
25 | Record safety controls during spraying: ventilation, PPE, and ignition control; evidence: toolbox talk record and daily checklist with signatures.
Comments
Filled by:
Signature:
Introduction |  |  | How to use this checklist
Apply vertical spray-applied membranes is the head term for this focused, field-ready quality checklist. It guides teams through spray waterproofing on vertical substrates, verifying uniform coverage, rebound control, adhesion, and long-term protection. The scope covers sprayed membrane systems (e.g., polyurea, elastomeric, cementitious spray-applied coating) installed on vertical elements only, and explicitly excludes brush/roller liquid-applied systems as well as unrelated horizontal works. By following these steps, you reduce risks of under-coverage, sagging, overspray, rebound waste, poor adhesion, blistering, and post-installation damage. You will capture measurable evidence—film-thickness readings, pull-off values, photos with scales, lot numbers, and sign-offs—so stakeholders can rely on traceable compliance per approved project specifications and authority requirements. The outcome is a durable, continuous vertical barrier integrated with penetrations and terminations, protected until concealment or service. Use this as a live, collaborative tool: tick items, add comments with photos, and export to PDF/Excel with a QR-secured record. |  |  | 1. Preparation: Review the approved data sheet, verify vertical scope only, assemble gauges (WFT/DFT), pull-off kit, PPE, masking, and calibrated environmental instruments. 2. Set up: Create or confirm an approved mock-up, calibrate equipment, and stage catch boards and protection before opening materials. 3. Using the Interactive Checklist: Start interactive mode, tick items in sequence, and add time-stamped comments with photos, readings, and lot numbers. 4. Evidence capture: Attach measurement logs, equipment calibration records, and close-up photos showing scales and defect repairs with retest results. 5. Export and share: Generate an export as PDF/Excel for review meetings and upload to the project document system. 6. Sign-off: Collect digital signatures from contractor, consultant, and client; archive the QR-authenticated record for compliance and warranty.